## links
SOW Tracking | System Project Documents | Charter
Project Request
3D Go-Live Master
SOW Tracking
Project Request
3D Go-Live Master
System Project Documents
Charter and other files

## System Project Backlog
| 2014-09-12 | [26 empty] | Content Dependency |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | June (P9) |  |  |  |  | July (P10) |  |  |  | August (P11) |  |  |  | September (P12) |  |  |  |  | October (P1 - 15) |  |  |  | November (P2 - 15) |  |  |  | December (P3 - 15) |  |  |  |  | January (P4 - 15) |  |  |  | February (P5 - 15) |  |  |  | March (P6 - 15) |  |  |  |  | April (P7 - 15) |  |  |  | May (P8 - 15) |  |  |  | June (P9 - 15) |  |  |  |  | July (P10 - 15) |  |  |  | August (P11 - 15) |  |  |  | September (P12 - 15)
Team | time axis 2013-11-25 to 2015-09-21
[12 empty] | Dates from sales team | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Status | Project Request? | Priority # | Project count | Program | Next Step | Product | Project | Opportunity Name | OPP # | Revenue associated: | Location | Sales Go-Live request Instal | Planned duration | TEAM | PM | On-site | SE Assigned | On-site | Trainer | On-site |  | Actual duration - Weeks | Initiation date | End of project date | % | Confidence level | Third Party | Owner-action item | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 2.004 | 2.004 | 2.004 | 2.004 | 2.004 | 2.004 | 2.004 | 4.007 | 4.007 | 4.007 | 4.007 | 4.007 | 4.007 | 4.007 | 4.007 | 4.007 | 3.006 | 4.007 | 5.009 | 3.005 | 3.005 | 3.005 | 2.004 | 2.004 | 2.004 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ACTIVE | Y | 1 | 1 |  | Go-Live Jun. 23; K signed; weekly follow call is now scheduled to track pending items. Parts orders and shipping prep in progress.--NEXT-Weekly progress meeting; Used part shipment has arrived to Panama - New parts shipment in progress. | CasinoLink | Star Bay Casino (P1) CL1.3 - C.004051 | SBX Library SBX 4.3 SP1 - CasinoLink 1.01 SP3 Casinolink 1.1 SP3 IVS 9.1 450 EGM (Estimated) -> 40 of them sbX IGT will work with their engineers to complete instalalation. IGT will train the trainer. Property will train the staff. Property will do the majority of the go live support and component installation. Property will acquire and configure their own servers. All games will connect to the system. | OPP55230 | 1251 | Panama | 2014-09-08 | 14 | 1 | Elvio Beautemps | 9/8 | Mario; Oscar | 9/8 | Edgar Trejo, Roxana or Katie? | 9/8 |  | 31.5714 | 2014-02-10 | 2014-09-19 |  | 100% | Synergy Blue (service window content) | As per customer installation should start by October 8th (go live around Oct.20th): 8/29/14 - Clifton told Elvio that the nuts and bolts to install the PTM Brackets did not arrived. He said that is the only part missing; Elvio told Clifton that the nuts and bolts sent were for the smib installation; Clifton already ordered the missing pieces and he expects to have them by mid-next week; Those came with 3 cut outs instead of 1 - Elvio is expediting internally the replacement of the 72 brackets; Marcelo and Luis informed Elvio about an error in the art sent. - Additionally Elvio is asking for the missing Logos/Graphics and text to complete the Art. The brackets for 72 IGT EGMs arrived wrongly. 1-Due to this delay, StarBay Go-Live date may cause a conflict with Crocs project preparation; best approach would be to split installation in two trips adding extra travel expenses of $ 9k, which IGT would absorb. Pendng Items: [MW] We need to do everything we can to recognize this revenue in Q4 a. We need to get agreement in writing that they will sign the SDI without the full opening of the casino b. We need to get commitment from both revrec and the customer in regards to the soft opening concept – can we do a final load test or something of that nature to achieve this objective? c. We need to get commitment from the customer that they will pay the balance within 10 days of this soft opening event | [11 empty] | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ACTIVE | Y | 2 | 1 |  | Go-Live Jun. 23; K signed; weekly follow call is now scheduled to track pending items. Parts orders and shipping prep in progress.--NEXT-Weekly progress meeting; Used part shipment has arrived to Panama - New parts shipment in progress. | CasinoLink | Star Bay Casino (P2) CL1.3 - C.004051 | SBX Library SBX 4.3 SP1 - CasinoLink 1.01 SP3 Casinolink 1.1 SP3 IVS 9.1 450 EGM (Estimated) -> 40 of them sbX IGT will work with their engineers to complete instalalation. IGT will train the trainer. Property will train the staff. Property will do the majority of the go live support and component installation. Property will acquire and configure their own servers. All games will connect to the system. | OPP55230 | 1251 | Panama | 2014-09-08 | 2 | 1 | Elvio Beautemps | 2014-10-15 | Mario; Emanuel (support) | 2014-10-15 | Roxana and Katie (Edgar shadow) | 10/15 |  | 37.5714 | 2014-10-17 | 2014-10-31 |  | 75% | Synergy Blue (service window content) | As per customer installation should start by October 8th (go live around Oct.20th): 8/29/14 - Clifton told Elvio that the nuts and bolts to install the PTM Brackets did not arrived. He said that is the only part missing; Elvio told Clifton that the nuts and bolts sent were for the smib installation; Clifton already ordered the missing pieces and he expects to have them by mid-next week; Those came with 3 cut outs instead of 1 - Elvio is expediting internally the replacement of the 72 brackets; Marcelo and Luis informed Elvio about an error in the art sent. - Additionally Elvio is asking for the missing Logos/Graphics and text to complete the Art. The brackets for 72 IGT EGMs arrived wrongly. 1-Due to this delay, StarBay Go-Live date may cause a conflict with Crocs project preparation; best approach would be to split installation in two trips adding extra travel expenses of $ 9k, which IGT would absorb. Pendng Items: [MW] We need to do everything we can to recognize this revenue in Q4 a. We need to get agreement in writing that they will sign the SDI without the full opening of the casino b. We need to get commitment from both revrec and the customer in regards to the soft opening concept – can we do a final load test or something of that nature to achieve this objective? c. We need to get commitment from the customer that they will pay the balance within 10 days of this soft opening event | 2014-10-20: 1.001; 2014-10-27: 1.001; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 3 | 1 |  | Waiting for contract signature | CasinoLink 1.4 | Crocs Casino CL1.4- R.1032 | Croc's Casino Resort - Jaco Beach, Costa Rica - Casinolink 146 EGMs | OPP69673 / OPP65633 |  |  | 2014-12-15 | 22 | 1 | Elvio Beautemps | 2014-12-15 | Adam Evans; Pablo Amarfil | 2014-12-15 | Katie (lead); 2nd trainer TBD | 2014-12-15 |  | 22 | 2014-07-21 | 2014-12-22 |  | 90% | Artwork; service window (TBD) | PMO: Elvio is working in the procurement list (Rory confirmed that we will have 153 machines; Rafael confirmed that the machines will be able to be shipped and delivered within the expected timeframe of Nov 1st ~ Nov 15th) -The services IGT team for the project was introduced to Croc’s in the weekly meeting. System Engineers: Pablo Amarfil (lead); Adam Evans Trainer: Katie Katayose (lead) | [34 empty] | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ACTIVE | Y | 4 | 1 |  | Elvio needs to place order before May in order to make the desired date by sales | Bonusing | Casino Club Rosario Bonusing - R.1035 | Xtra credit point play | OPP70509 / 74894 |  | Argentina | TBD | 7 | 2 | Norberto Acevedo | 2014-09-22 | Emanuel | 2014-09-22 | Roxana | 2014-09-22 |  | 9.4286 | 2014-07-18 | 2014-09-22 |  | 95% |  | Casino Rosario A. Casino will enable and configure Legacy bonusing on all machines including IGT owned. B. Training facility and machines are reserved for onsite training. C. Trainer/SE tested menu code in lab is working as client requested. Project is progressing as planned, week of 9/22 – 9/26. | [34 empty] | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ACTIVE | N | 5 | na | na |  | Floor Config (SE Task) | Operadora Jubilee (SE Task_Game theme/Floor config) | [5 empty] | 0.5 | 4 | MW / Kay |  | Kayode | 2014-09-22 |  |  |  | 0.5 | 2014-09-22 | 2014-09-25 12:00 |  |  | Cloud 2.0 |  | 2014-09-22: 1.004; 2014-09-29: 0; 2014-10-06: 0; 2014-10-13: 0; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 6 | 1 |  | Waiting on customer date confirmation | Advantage DEMO | Casino Club Outing Activity DEMO | Internal Adv 9.1 | OPP66750, OPP56258, OPP56259, OPP53285, OPP40800 |  |  | TBD | 2.5 | 1 | Elvio Beautemps |  | Pablo* | TBD | Roxana | 2014-09-29 |  | 2.5 | 2014-09-29 | 2014-10-16 12:00 |  | 50% | G2E Artwork |  | 2014-09-29: 1.001; 2014-10-06: 1.001; 2014-10-13: 1.001; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 7 | 1 | p1 |  | Cloud 2.0 | Operadora Jubilee Cloud 2.0 Upgrade - R.2004 | [5 empty] | 1.5 | 2 | Norberto Acevedo |  | Maya/Kay | 2014-09-29 |  |  |  | 1 | 2014-09-29 | 2014-10-06 |  |  | Cloud 2.0 |  | 2014-09-29: 1.002; 2014-10-06: 1.002; 2014-10-13: 0; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 8 | 0 | p2 |  | Cloud 2.0 | Operadora New York Cloud 2.0 Upgrade - R.2005 | [5 empty] | 1.5 | 2 | Norberto Acevedo |  | Maya/Kay | 2014-09-29 |  |  |  | 1.5 | 2014-09-29 | 2014-10-06 |  |  | Cloud 2.0 |  | 2014-09-29: 1.002; 2014-10-06: 1.002; 2014-10-13: 0; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 9 | 0 | p3 |  | Cloud 2.0 | Operadora Paradise Cloud 2.0 Upgrade - R.2006 | [5 empty] | 1.5 | 2 | Norberto Acevedo |  | Maya/Kay | 2014-09-29 |  |  |  | 1 | 2014-09-29 | 2014-10-06 |  |  | Cloud 2.0 |  | 2014-09-29: 1.002; 2014-10-06: 1.002; 2014-10-13: 0; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 10 | 0 | p4 |  | Cloud 2.0 | Operadora Providens Cloud 2.0 Upgrade - R.2007 | [5 empty] | 1.5 | 2 | Norberto Acevedo |  | Maya/Kay | 2014-09-29 |  |  |  | 1 | 2014-09-29 | 2014-10-06 |  |  | Cloud 2.0 |  | 2014-09-29: 1.002; 2014-10-06: 1.002; 2014-10-13: 0; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 11 | 0 | p5 |  | Cloud 2.0 | Operadora Viva Mexico Cloud 2.0 Upgrade - R.2008 | [5 empty] | 1.5 | 2 | Norberto Acevedo |  | Maya/Kay | 2014-09-29 |  |  |  | 1 | 2014-09-29 | 2014-10-06 |  |  | Cloud 2.0 |  | 2014-09-29: 1.002; 2014-10-06: 1.002; 2014-10-13: 0; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 12 | 1 | p1 |  | Cloud 2.0 | Manteo Rivera Cloud 2.0 Upgrade - R.2002 | Cloud Rivera | OPP53334 |  | Uruguay | 2014-04-01 | 1.5 | 2 | Norberto Acevedo |  | Emanuel | 2014-10-06 |  |  |  | 4 | 2014-10-06 | 2014-10-10 |  |  | Cloud 2.0 Firewall |  | 2014-10-06: 1.002; 2014-10-13: 0; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 13 | 0 | p2 |  | Cloud 2.0 | Manteo Sala Esparcimiento Cloud 2.0 Upgrade - R.2003 | Cloud Rivera | OPP53334 |  | Uruguay | 2014-04-01 | 1.5 | 2 | Norberto Acevedo |  | Emanuel | 2014-10-06 |  |  |  | 4 | 2014-10-06 | 2014-10-10 |  |  | Cloud 2.0 Firewall |  | 2014-10-06: 1.002; 2014-10-13: 0; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
1 | ACTIVE | Y | 14 | 1 |  |  | LABS | IGT LABS SETUP - Internal Project LAC | Labs assessment for all LAC |  |  |  | 2014-11-20 | 24.9 | 3 | Gustavo Schleider |  | Adan;Mario;PabloAm |  |  |  |  | 24.9 | 2014-05-30 | 2014-11-20 07:12 |  | 50% | IT for configuration | LAB Argentina - waiting for parts LAB Mexico - waiting for parts LAB Weston - parts arrived | [27 empty] | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | BACKLOG | Y | 14.5 | na | na |  | SMIB | Entretenimientos Patagonia [Legacy SMIB firmware upgrade] | [5 empty] | 1.4 | 1 | MW / Kay | [6 empty] | 0.5 | 2014-10-01 | 2014-10-10 19:12 |  |  | Cloud 2.0 | Sales - contract not signed | 2014-10-06: 1.001; 2014-10-13: 0; 2014-10-20: 0; 2014-10-27: 0; 2014-11-03: 0; 2014-11-10: 0; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
3 | BACKLOG | N | 15 | 0 |  |  | EZPAY Re-install | Vidaplan Nogaro Re-install | Instalacion EZPay 60 egms |  |  |  | TBD | 7 | 1 | Elvio Beautemps | [6 empty] | 7 | 2014-11-03 | 2014-12-22 |  |  |  | Customer requesting EZPAY re-install first Waiting for customer response to confirm dates | 2014-11-03: 1.001; 2014-11-10: 1.001; 2014-11-17: 1.001; 2014-11-24: 1.001; 2014-12-01: 1.001; 2014-12-08: 1.001; 2014-12-15: 1.001; 2014-12-22: 1.001; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
3 | BACKLOG | N | 16 | 0 |  | Grupo Sam has requested we prepare a project to migrate to 9.1. They require the migration to be complete within Calendar year 2014. | Advantage Upgrade | Grupo SAM Upgrade | (Upgrade) Advantage 9.1 Upgrade sbX to compatible version for service window (Number of sites: 9) |  |  | San Isidro, Lima y Callao Peru | TBD | 16 | 1 | Elvio Beautemps | [6 empty] | 16 | 2014-11-03 | 2015-02-23 |  |  |  | 1- dates still being assessed (PM beginning with scope definition) 2- Revenue | 2014-11-03: 1.001; 2014-11-10: 1.001; 2014-11-17: 1.001; 2014-11-24: 1.001; 2014-12-01: 1.001; 2014-12-08: 1.001; 2014-12-15: 1.001; 2014-12-22: 1.001; 2014-12-29: 1.001; 2015-01-05: 1.001; 2015-01-12: 1.001; 2015-01-19: 1.001; 2015-01-26: 1.001; 2015-02-02: 1.001; 2015-02-09: 1.001; 2015-02-16: 1.001; 2015-02-23: 1.001; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
3 | BACKLOG | N | 17 | 0 |  |  | CasinoLink Upgrade | Embassy Suites Upgrade 1.3 | Embassy Suites Upgrade to 1.2 | Upgrade to 1.2 |  |  | TBD | 16 | 2 | Norberto Acevedo | [6 empty] | 16 | 2014-11-03 | 2015-02-23 |  |  |  | Norberto will follow up with Compliance on approval of 1.3 | 2014-11-03: 1.002; 2014-11-10: 1.002; 2014-11-17: 1.002; 2014-11-24: 1.002; 2014-12-01: 1.002; 2014-12-08: 1.002; 2014-12-15: 1.002; 2014-12-22: 1.002; 2014-12-29: 1.002; 2015-01-05: 1.002; 2015-01-12: 1.002; 2015-01-19: 1.002; 2015-01-26: 1.002; 2015-02-02: 1.002; 2015-02-09: 1.002; 2015-02-16: 1.002; 2015-02-23: 1.002; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
3 | BACKLOG | N | 18 | 0 |  |  | EZPAY 1.9.2 Upgrade | Dreams Chile Upgrade |  |  |  | Chile | TBD | 8 | 1 | Elvio Beautemps | [6 empty] | 8 | 2014-11-03 | 2014-12-29 |  |  |  | 1- dates still being assessed (PM beginning with scope definition) 2- Revenue? | 2014-11-03: 1.001; 2014-11-10: 1.001; 2014-11-17: 1.001; 2014-11-24: 1.001; 2014-12-01: 1.001; 2014-12-08: 1.001; 2014-12-15: 1.001; 2014-12-22: 1.001; 2014-12-29: 1.001; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
5 | HOLD | Y | na | 0 | p1 | Elvio needs to place order before May in order to make the desired date by sales | Bonusing | Casino Club Puerto Madero (CIESA) Bonusing - R.1036 | Xtra credit point play | OPP70509 / 74894 | $ 1,281k | Argentina | TBD | 7 | 2 | Norberto Acevedo |  | Emanuel | 2014-09-01 | Katie, Roxana (shadows) | 2014-09-01 |  | 7 | 2014-11-03 | 2014-12-22 |  |  | MenuCode | Sales dependency - Puerto Madero (CIESA) - project placed on hold until further notice due to audit by regulato (customer is unable to continue with installation) | 2014-11-03: 1.002; 2014-11-10: 1.002; 2014-11-17: 1.002; 2014-11-24: 1.002; 2014-12-01: 1.002; 2014-12-08: 1.002; 2014-12-15: 1.002; 2014-12-22: 1.002; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
5 | HOLD | Y | na | 0 |  |  | EZPAY IVS Upgrade | Vidaplan Nogaro EZPUpgrade - R.2001 | Reinstalacion Upgrade de IVS EZPay c Spielo |  |  |  | TBD | 12 | 1 | Elvio Beautemps | 10/6 - 10/7 | Pablo Amarfil; Emilio Pagano | 2014-10-06 | Roxana Di Franco | 2014-10-06 |  | 12 | 2014-11-03 | 2015-01-26 |  |  | na | Sales dependency: - upgrade on hold as customer is requesting re-installation of EZPAY system before upgrade. | 2014-11-03: 1.001; 2014-11-10: 1.001; 2014-11-17: 1.001; 2014-11-24: 1.001; 2014-12-01: 1.001; 2014-12-08: 1.001; 2014-12-15: 1.001; 2014-12-22: 1.001; 2014-12-29: 1.001; 2015-01-05: 1.001; 2015-01-12: 1.001; 2015-01-19: 1.001; 2015-01-26: 1.001; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
5 | HOLD | N | na | 0 |  | Waiting for contract signature | sbx | Inmobiliaria Masaris Sac Participaciones del Pacifico | Masaris-Peru-Cloud | OPP57219 |  | Peru | TBD | 9 |  | SALES |  | Oscar Gomez |  |  |  |  | 9 | 2014-11-03 | 2015-01-05 |  |  |  | Sales (no contract) | 2014-11-03: 1.0001; 2014-11-10: 1.0001; 2014-11-17: 1.0001; 2014-11-24: 1.0001; 2014-12-01: 1.0001; 2014-12-08: 1.0001; 2014-12-15: 1.0001; 2014-12-22: 1.0001; 2014-12-29: 1.0001; 2015-01-05: 1.0001; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
5 | HOLD |  | na | 0 | p1 | Waiting for contract signature | Cloud | Fiesta Casino Presidente Casino Pajaro Trueno a/c3116305. San Jose, Costa Rica - R.1033 | Fiesta Casino Cloud | OPP70231 |  | Holiday Inn Downtown - Aurola. Costa Rica | 2014-10-22 | 10 | 2 | Norberto Acevedo | 2014-08-25 | Oscar Gomez | 2014-08-25 | Edgar Trejo | 2014-08-25 |  | 10 | 2014-11-03 | 2015-01-12 |  |  | AdMgr | Sales dependency: - no contract | 2014-11-03: 1.002; 2014-11-10: 1.002; 2014-11-17: 1.002; 2014-11-24: 1.002; 2014-12-01: 1.002; 2014-12-08: 1.002; 2014-12-15: 1.002; 2014-12-22: 1.002; 2014-12-29: 1.002; 2015-01-05: 1.002; 2015-01-12: 1.002; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
5 | HOLD |  | na | 0 | p2 | Waiting for contract signature | Cloud | Fiesta Casino Aurola Thunderbird Estellas del Caribe- a/c3116294-San Jose, Costa Rica - R.1034 | Fiesta Casino Cloud | OPP70231 / OPP72236 |  |  | 2014-10-23 | 10 | 2 | Norberto Acevedo | 2014-08-25 | Oscar Gomez | 2014-08-25 | Edgar Trejo | 2014-08-25 |  | 10 | 2014-11-03 | 2015-01-12 |  |  | AdMgr | Sales dependency: - no contract | 2014-11-03: 1.002; 2014-11-10: 1.002; 2014-11-17: 1.002; 2014-11-24: 1.002; 2014-12-01: 1.002; 2014-12-08: 1.002; 2014-12-15: 1.002; 2014-12-22: 1.002; 2014-12-29: 1.002; 2015-01-05: 1.002; 2015-01-12: 1.002; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
6 | COMPLETED |  | x | 0 | p1 | Go-Live May 1 - K signed-Elvio ordered bootprom (waiting on delivery dates); - contract may be signed already?-- (need to order parts) | SBX | Samcorp - Golden Investment | GI-Peru-Sbx-50units | OPP55020 |  | Peru | 2014-04-23 | 10 | 1 | Elvio Beautemps | na | Oscar Gomez | 5/5 - 5/14 | Edgar Trejo | 5/5 - 5/14 |  | 18 | 2014-02-17 | 2014-06-23 |  | 100% |  | PMO | [12 empty] | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p2 | Go-Live May 1 - K signed-Elvio ordered bootprom (waiting on delivery dates); - contract may be signed already?-- (need to order parts) | SBX | Samcorp - Golden Gaming Hacienda | Sbx 4.1 hot fix-patch3 with Analytics-50units | OPP71248 |  | Peru | 2014-04-23 | 8 | 1 | Elvio Beautemps | na | Oscar Gomez | 5/5 - 5/14 | Edgar Trejo | 5/5 - 5/14 |  | 18 | 2014-02-17 | 2014-06-23 |  | 100% |  | PMO | [12 empty] | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 |  | 1. Elvio working with CS parts to get harnessing to display UGA1.2, parts shipped today ( 25th March) 2. If hardware arrives on time to display UGA1.2, no additional software required 3 Martin got UGA 1.1 operation with same art, still got minor details to resolve 4 Martin to coordinate with Julie for training on any items were he has concerns 5 Services to give Presales a demo on system week of 8 April 6 Elvio to follow up with FS to ensure EGM are in good condition 7 Mike Mc confirmed current date for demo May 5-6 Please let me know if I omitted anything from today’s meeting, currently no road blocks to make the desired dates | UGA | IGT Argentina (SAGSE program) | ARG Internal UGA Advantage |  |  |  |  | 28 | 1 | Elvio Beautemps |  | P.Amarfil; E.Pagano | 4/21; 5/5 | NA |  |  | 45.1429 | 2013-08-08 | 2014-06-20 |  | 99% |  | PMO | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 |  | U.S. to train Latin America team (Stu Reis) | Healthcheck | Hotelera Emprender - Analytics HealthCheck | HEALTHCHECK (1 SE required for support) |  |  |  |  | 2 | 5 | Gustavo Schleider |  | Emilio Pagano |  |  |  |  | 3 | 2014-06-09 | 2014-06-30 |  | 100% |  | Gus | [28 empty] | 1.005 | 1.005 | 1.005 | 1.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 |  | Pending parts: 90% complete (Horacio will get status) | UGA | IGT Mexico (working on 1.0; progress1.2) | MX Internal - UGA |  |  |  |  | 26 | 3 | Horacio Garcia |  | Kayode |  | NA |  |  | 33.7143 | 2013-10-25 | 2014-06-18 |  | 100% |  | PMO | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p1 | ready to start-contrac signed; Elvio spoke to customer who said is ready to start (pending connection) | Cloud | Manteo - Casino Rivera | Cloud Rivera | OPP53334 |  | Uruguay | 2014-04-01 | 4 | 1 | Elvio Beautemps | na | Emilio Pagano | 5/26 - 6/2 | Roxana | 5/26 - 6/2 |  | 4 | 2014-05-19 | 2014-06-16 |  | 100% |  | PMO | [25 empty] | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p2 | ready to start-contrac signed (Elvio will speak with customer this week) | Cloud | Manteo - Sala de Esparcimiento | Cloud Rivera Esparcimiento | OPP70115 |  | Uruguay | 2014-04-07 | 4 | 1 | Elvio Beautemps | na | Emilio Pagano | 5/26 - 6/2 | Roxana | 5/26 - 6/2 |  | 4 | 2014-05-19 | 2014-06-16 |  | 100% |  | PMO | [25 empty] | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 |  | Pending resources from cloud team: 10% complete (hardware ready; team to be assigned - SE from NJ) | Cloud | IGT Mexico | MX Internal - UGA |  |  |  |  | 16 | 3 | Horacio Garcia |  | J.P.Maya |  | NA |  |  | 17.5714 | 2014-01-06 | 2014-05-09 |  | 100% |  | PMO | [6 empty] | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p3 | Pending SMA change request by Elvio's - transitioin to support | Advantage | Newport - Casino Installation SamCorp [Golden Investment S.A.] | Bonusing 2080 XC y PP | OPP66705 |  | Peru | 2014-03-31 | 6 | 1 | Elvio Beautemps | na | na | na | na | na |  | 9.5714 | 2014-02-17 | 2014-04-25 |  | 100% |  | PMO | [12 empty] | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 |  | waiting on update by Martin Kutter | Cloud | IGT Argentina | ARG Internal - sbX Cloud Lab Install |  |  |  | 2014-01-08 | 2 | 1 | Elvio Beautemps |  | Pagano |  | NA |  |  | 2.4286 | 2014-03-11 | 2014-03-28 |  | 100% |  | PMO | [16 empty] | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p4 | Installation completed and SDIs were signed 3/12/2014 - | Advantage | Golden Palace - Bonusing Samcorp Lab [Golden Gaming S.A.] | GG-Peru-Bonusing 388 | OPP62945 |  | Peru | 2014-03-04 | 4 | 2 | Juan Di Feo | [6 empty] | 3.2857 | 2014-02-17 | 2014-03-12 |  | 100% |  | PMO | [12 empty] | 1.002 | 1.002 | 1.002 | 1.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p5 | testing in production | Advantage | La Hacienda - Casino Installation SamCorp [Golden Investment S.A.] | Bonusing 870 XC y PP | OPP66700 |  | Peru | 2014-03-11 | 5 | 2 | Juan Di Feo | [6 empty] | 4.4286 | 2014-02-17 | 2014-03-20 |  | 100% |  | PMO | [12 empty] | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 |  |  | Advantage | Dania Casino & Jai-Alai | Advantage | OPP59401 |  | Florida | 2014-02-17 | 16 | 1 | Elvio Beautemps | [6 empty] | 17.7143 | 2013-10-27 | 2014-02-28 |  | 100% |  | PMO | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p1 |  | CasinoLink | CET - Rio Ceballos (3rd Install) | Casinolink Rio Ceballos | OPP65492 (same as carlos Paz) |  | Cordoba | 2014-02-07 | 1.5 | 4 | Gustavo Schleider | [6 empty] | 3.6429 | 2014-01-26 12:00 | 2014-02-21 |  | 100% |  | PMO | [9 empty] | 1.004 | 1.004 | 1.004 | 1.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 |  |  | TITO | IGT Argentina | ARG Internal - TITO System Licensing project |  |  |  |  | 28 | 1 | Elvio Beautemps | [6 empty] | 28 | 2013-08-15 | 2014-02-27 |  | 100% |  | PMO | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p1 |  | Cloud | New York Monterrey | Operadora Class Cloud Mtey New York | OPP63816 |  | Nuevo Leon | 2013-11-30 | 6 | 3 | Horacio Garcia | [6 empty] | 14.1429 | 2013-10-19 | 2014-01-26 |  | 100% |  | PMO | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p2 |  | CasinoLink | CET S.A. | CET - Casinolink Carlos Paz I | OPP65492 |  | Cordoba | 2013-12-06 | 12 | 2 | Juan Di Feo | [6 empty] | 17.1429 | 2013-09-13 | 2014-01-11 |  | 100% |  | PMO | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p2 |  | Cloud | Viva Mexico | Operadora Class Cloud Mtey Viva Mexico | OPP63814 |  | Monterrey | 2014-01-25 | 12 | 3 | Horacio Garcia | [6 empty] | 10.5714 | 2013-10-25 | 2014-01-07 |  | 100% |  | PMO | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | COMPLETED |  | x | 0 | p3 |  | Cloud | Paradise Monterrey & Jubilee | Operadora Class Cloud Mtey Paradise | OPP63815 |  | Monterrey | 2013-11-30 | 6 | 3 | Horacio Garcia | [6 empty] | 8.7143 | 2013-10-19 | 2013-12-19 |  | 100% |  | PMO | 1.003 | 1.003 | 1.003 | 1.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CANCELLED | Y | xx | 0 |  |  | Advantage Demo | SAGSE - Demo |  |  |  |  | TBD | 10 | 1 | Elvio Beautemps |  | Emilio Pagano | 2014-11-10 | Roxana | 2014-11-10 |  | 11.5714 | 2014-08-25 | 2014-11-14 |  |  | na |  | 2014-08-25: 1.001; 2014-09-01: 1.001; 2014-09-08: 1.001; 2014-09-15: 1.001; 2014-09-22: 1.001; 2014-09-29: 1.001; 2014-10-06: 1.001; 2014-10-13: 1.001; 2014-10-20: 1.001; 2014-10-27: 1.001; 2014-11-03: 1.001; 2014-11-10: 1.001; 2014-11-17: 0; 2014-11-24: 0; 2014-12-01: 0; 2014-12-08: 0; 2014-12-15: 0; 2014-12-22: 0; 2014-12-29: 0; 2015-01-05: 0; 2015-01-12: 0; 2015-01-19: 0; 2015-01-26: 0; 2015-02-02: 0; 2015-02-09: 0; 2015-02-16: 0; 2015-02-23: 0; 2015-03-02: 0; 2015-03-09: 0; 2015-03-16: 0; 2015-03-23: 0; 2015-03-30: 0; 2015-04-06: 0; 2015-04-13: 0; 2015-04-20: 0; 2015-04-27: 0; 2015-05-04: 0; 2015-05-11: 0; 2015-05-18: 0; 2015-05-25: 0; 2015-06-01: 0; 2015-06-08: 0; 2015-06-15: 0; 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 0; 2015-07-13: 0; 2015-07-20: 0; 2015-07-27: 0; 2015-08-03: 0; 2015-08-10: 0; 2015-08-17: 0; 2015-08-24: 0; 2015-08-31: 0; 2015-09-07: 0; 2015-09-14: 0; 2015-09-21: 0
7 | CANCELLED |  | xx | 0 |  | Pending answer from Celene | EZ Pay Standalone | La Cabana Beach & Raquet Club Hotel | Glitz Promo Ticket Licence | OPP55656 |  |  | TBD | 1 | 0 | SALES | [6 empty] | 0 | [5 empty] | sales (block) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
7 | CANCELLED | N | xx | 0 |  |  | EZPAY IVS | Vidaplan Mantra Upgrade | Instalacion EZPay 60 egms |  |  |  | TBD | 7 | 1 | Elvio Beautemps | [6 empty] | 7 |  | 1900-02-17 |  |  |  | 1- likely for March 2015 - Sales (no contract) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.001
6 | COMPLETED |  | xx | 0 |  | Pending update from Chris (CN's) | CasinoLink | ALL LATAM CL CUSTOMERS | several one week projects |  |  |  |  | 20 | 1 | Elvio Beautemps | [6 empty] | 20 |  | 1900-05-19 |  |  |  | cn released | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.001
6 | COMPLETED |  | xx | 0 |  |  | CasinoLink | IGT Argentina | Homologacion Casinolink en la Povincia de Buenos Aires |  |  |  | 2013-11-13 | 12 | 1 | Elvio Beautemps | [6 empty] | 12 |  | 1900-03-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.001
7 | CANCELLED | N | xx | 0 |  | McBide: we will be presenting a Cloud migration proposal to Televisa in Mex for their 8 sbX sites. Target go-live would be September, 2 Sites per week (complete before FY close). For the time being we need the following (requested by 03/26): 1. High-level work plan for the migration, can it be done in the timeframe allotted. 2. Provide drop-dead date when contract would need to be signed in order to meet September go-live. Negotiations with Televisa will take place in April or May. we will be presenting a Cloud migration proposal to Televisa in Mex for their 8 sbX sites. Target go-live would be September, 2 Sites per week (complete before FY close). For the time being we need the following (requested by 03/26): 1. High-level work plan for the migration, can it be done in the timeframe allotted. 2. Provide drop-dead date when contract would need to be signed in order to meet September go-live. Negotiations with Televisa will take place in April or May. | Cloud 2.0 | Televisa in Mex. 8 sbX sites | OPP71490 OPP71492 OPP71493 OPP71494 OPP71495 OPP71496 OPP71497 OPP71498 | OPP71490 OPP71492 OPP71493 OPP71494 OPP71495 OPP71496 OPP71497 OPP71498 |  |  | TBD | 12 | 0 | SALES |  | J.P.Maya |  |  |  |  | 12 |  | 1900-03-24 |  |  |  | Sales Working on a commitment to migrate Televisa's 8 sbX to Cloud to improve their service level and reduce our opex to support; 7/11/2014 - Services elements are now confirmed, starting internal review of deal week of 7/7. o NEXT STEP: Submit proposal (Target 7/16) and schedule EBC visit. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
7 | CANCELLED |  | xx | 0 |  |  | CasinoLink Upgrade | Veneto | INTELLINGE SUITE UPGRADE |  |  |  | TBD | 1 | 0 | SALES | [6 empty] | 1 |  | 1900-01-06 |  |  |  | sales (block); all support stopped for cust; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
7 | CANCELLED |  | xx | 0 |  |  | SBX Upgrade | CIRSA MEXICO CASINO LIVE DEL VALLE | 4.3 HOT FIX 11 UPGRADE |  |  |  | TBD | 3 | 0 | SALES | [6 empty] | 3 |  | 1900-01-20 |  |  |  | Cancelled due to customer looking to remove system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
7 | CANCELLED |  | xx | 0 |  |  | DTO | Juan Di Feo |  |  |  |  | TBD | 0.9 | 1 | Elvio Beautemps | [6 empty] | 0.9 | 2014-02-25 | 2014-03-03 07:12 |  |  |  | PMO | [14 empty] | 1.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CANCELLED |  | xx | 0 |  | Meeting next week to redefine scope. | SBX | Mendoza Roadshow (DEMO) | DEMO | [5 empty] | 1 | Elvio Beautemps | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.001
7 | CANCELLED |  | xx | 0 |  | need to evaluate; create charter | TITO | IGT - MCLAC (Review licenses) | TITO LICENSE EVALUATION | na |  |  |  | 8 | 1 | Elvio Beautemps |  | P.Amarfil; Emanuel |  | Not needed | Not needed | Not needed | 8 |  | 1900-02-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.001
7 | CANCELLED |  | xx | 0 |  |  | CasinoLink | CET - LaFalda (4th Install) --> {60 days after 3rd install} | Need opp created by Bobbio/Pagani |  |  | Cordoba | 2014-04-15 | 5 |  | SALES | [6 empty] | 4.5714 | 2014-03-10 | 2014-04-11 |  | 0% | [17 empty] | 1.0001 | 1.0001 | 1.0001 | 1.0001 | 1.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CANCELLED |  | xx | 0 |  |  | CasinoLink | CET - Altagracia (5th Install) -->{60 days after 4th install} | CET -need opp created Bobbio/Pagani |  |  | Cordoba |  | 6 |  | SALES | [6 empty] | 5.5714 |  | 1900-02-07 |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
7 | CANCELLED |  | xx | 0 |  |  | Cloud | Codere & Loteria (Buenos Aires) | DEMO | cancelled? |  | Buenos Aires | 2014-02-10 | 1 |  | SALES | [6 empty] | 1 |  | 1900-01-06 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
7 | CANCELLED |  | xx | 0 |  |  |  |  | DEMO | cancelled? |  | Buenos Aires | 2014-02-10 |  |  | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
4 | REQUEST |  |  | 0 | [11 empty] | SALES | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0001
Next available project start date
Florencia Bobbio: 2 Decision Makers of Casino Club will be on Holidays during april.
Is there any chance to move the project to May?
)
CET 4TH Install - GoLive scheduled to 5/2/14 *** (Review agreement: 60 days after 3RD install should be 4/15/14)
CET 5TH Install - GoLive sch. 7/15/14 - (60 days after 4TH install)
Next available date: November 3rd
    NJ Data Center closing October 31
Note on AF4: Doug.Simpson@IGT.com (Content) Raymond.Dickenson@IGT.com (Menu Code)
Note on R5: 12 weeks project + 2weeks added as per Mike and Otto (post go live support)
Note on Q10: IGTAdmin: 4/7 date is hard stop; subject to travel from U.S.
Note on K42: IGTAdmin: Rodenberg.Otto 8:10 AM Hello Elvio on leave this week ,in the Change request the intended go live dates are shown CET S.A. (Villa Carlos Paz) 2/11/2014 CET S.A. (La Falda) 4/18/2014 Rio Ceballos VIP 7/15/2014 CET S.A. (Alta Gracia) 11/11/2014 dated between Carlos paz aND rIO NEED TO BE SWAPED
Note on H49: LUIS: From: Rodenberg.Otto Sent: Friday, March 14, 2014 1:57 PM To: Vazquez.Elizabeth; Sierra.Celene Cc: McBride.Mike; Stewart.Chris; Rivera.Domingo; Baque.Luis Subject: RE: sign training SO 780804 La Cabana Hello Celene Has the situation with Glitz been resolved ? We still got two open projects pending 1 Casinolink training 2 Installation of TITO Promo tickets - OPP55656 Regards Otto
Note on H51: LUIS: 1 CORDOBA ;4 BARILOCHE; 1 PANAMA; 1 PR; 1 HONDURAS
Note on K52: IGTAdmin: From: Rodenberg.Otto Sent: Friday, January 17, 2014 8:59 AM To: Schleider.Gustavo; McBride.Mike Cc: Di Feo.Juan; Pagani.Fernando; Amarfil.Pablo; Osores.Emiliano; Beautemps.Elvio; Corio.Esteban; Willis.Mike; Baque.Luis Subject: RE: Homologation Casinolink Loteria de la provincia de Buenos Aires- January 7 - 2014In the managers' meeting, to be held on 7 and 8 January, they will speak what are the next steps in this project Hello As agreed during the meeting this morning, the PMO team will be placing the project on hold and this will be driven by both Mike & Gus Regards Otto From: Schleider.Gustavo Sent: Thursday, January 16, 2014 4:49 PM To: Rodenberg.Otto; McBride.Mike Cc: Di Feo.Juan; Pagani.Fernando; Amarfil.Pablo; Osores.Emiliano; Beautemps.Elvio; Corio.Esteban; Willis.Mike; Baque.Luis Subject: Re: Homologation Casinolink Loteria de la provincia de Buenos Aires- January 7 - 2014In the managers' meeting, to be held on 7 and 8 January, they will speak what are the next steps in this project Hi, Otto. I'm having a meeting with BVision next Tuesday to discuss the development. A PM still will need to track progress, as this is only information that we are researching. Thanks. Gus. -----Original Message----- From: Rodenberg.Otto Sent: Thursday, January 16, 2014 01:30 PM Pacific Standard Time To: McBride.Mike Cc: Di Feo.Juan; Schleider.Gustavo; Pagani.Fernando; Amarfil.Pablo; Osores.Emiliano; Beautemps.Elvio; Corio.Esteban; Willis.Mike; Baque.Luis Subject: RE: Homologation Casinolink Loteria de la provincia de Buenos Aires- January 7 - 2014In the managers' meeting, to be held on 7 and 8 January, they will speak what are the next steps in this project Hello Do we need to continue with the assignation of a project manager to track this case ? if so how long, as this will affect the intake of new system projects Thanks Otto From: McBride.Mike Sent: Thursday, January 16, 2014 4:27 PM To: Rodenberg.Otto Cc: Di Feo.Juan; Schleider.Gustavo; Pagani.Fernando; Amarfil.Pablo; Osores.Emiliano; Beautemps.Elvio; Corio.Esteban; Willis.Mike; Baque.Luis Subject: Re: Homologacion Casinolink Loteria de la provincia de Buenos Aires- January 7 - 2014In the managers' meeting, to be held on 7 and 8 January, they will speak what are the next steps in this project We are waiting for an update from the Argentina systems team re:development of interface from BVision. -Mike On Jan 16, 2014, at 4:25 PM, "Rodenberg.Otto" <Otto.Rodenberg@IGT.com> wrote: Hello Mike McBride Could you please confirm if the PMO need to continue tracking this project ( take on of the project positions within the capacity plan) or we can move the status to on hold under we hear further form your team ? Thanks Otto From: Di Feo.Juan Sent: Tuesday, January 07, 2014 3:09 PM To: McBride.Mike; Schleider.Gustavo; Pagani.Fernando; Amarfil.Pablo; Osores.Emiliano; Beautemps.Elvio; Rodenberg.Otto; Corio.Esteban; Willis.Mike Subject: Homologacion Casinolink Loteria de la provincia de Buenos Aires- January 7 - 2014In the managers' meeting, to be held on 7 and 8 January, they will speak what are the next steps in this project Hello Attached you can see the status report for this project Monday January 7th, 2014 Gustavo is in charge to find out the cost and the time it takes to develop the interface with BVision m People An email was sent to the Lottery people to inform we will need to postpone the meeting that was scheduled for January 17 for later Mike McBride will communicate with people from Engineering to consult on the development of the interface In the managers' meeting, to be held on 7 and 8 January, they will speak what are the next steps in this project Please, let me know if you have any doubts Thanks Juan Martin Di Feo Project Manager ¦ Latin America and Caribbean ¦ International Game Technology Emilio Frers 2154 ¦ Martínez (1640), Provincia de Buenos Aires Office: +54.11.4500.3944 Mobile: +54.9.11.3561 0696 juan.difeo@igt.com
Note on H53: LUIS migrate Televisa's 8 sbX to Cloud to improve their service level and reduce our opex to support.
Note on K53: IGTAdmin: IGT will pay all migration costs to Cloud, including Cachebox and professional services IGT will continue to offer monitoring and OT execution Televisa will pay a new fee negotiated as part of Cloud contract

## System Supply & Demand Analysis (hidden)
[5 empty] | AVAILABLE CAPACITY | [5 empty] | 77% | AVAILABLE HOURS CALCULATED: (2080 HOURS/YEAR) x (77%)
|  |  |  | Headcount |  |  |  | Hours
| Actual | Installations | Upgrades | Support | Managed Services | Available | Installations | Upgrades | Support | Managed Services
| Headcount | 22.68 | 5.88 | 294 | 228.48 | Hours | 22.68 | 5.88 | 294 | 228.48
PM | 3 | 2.016 | 0.35175 | 0.3675 | 0.05124 | 4804.8 | 3476.2288 | 606.5295 | 633.6875 | 88.3541
SE | 12 | 3.7012 | 0.70875 | 5.2185 | 0.5124 | 19219.2 | 7014.6697 | 1343.2346 | 9890.1868 | 971.1089
TRN | 3 | 3.3547 | 0.714 | 0.91875 | 0.05124 | 4804.8 | 3198.9947 | 680.8502 | 876.094 | 48.861
Current Available Capacity | 18 | 9.0641 | 1.7745 | 6.5047 | 0.61488 | 28828.8 | 14544.4704 | 2847.3971 | 10437.6478 | 986.6484
84.16%
OPTIMUM CAPACITY DEMAND (FY13 Effort)
|  |  | Headcount Demand |  |  |  |  | Hours
| Needed | Installations | Upgrades | Support | Managed Services | Available | Installations | Upgrades | Support | Managed Services |  | Demand % (utilization)
| Headcount | 27 | 7 | 350 | 272 | Hours | 27 | 7 | 350 | 272 |  | Installations | Upgrades | Support | Managed Services | total
PM | 3.3172 | 2.4 | 0.41875 | 0.4375 | 0.061 | 5312.9076 | 3829.7812 | 670.8375 | 700.875 | 97.722 |  | 72.35% | 12.62% | 13.19% | 1.839% | 100%
SE | 12.0725 | 4.4062 | 0.84375 | 6.2125 | 0.61 | 19335.316 | 7058.8125 | 1351.6875 | 9952.425 | 977.22 |  | 36.5% | 6.989% | 51.46% | 5.053% | 100%
TRN | 5.9985 | 3.9937 | 0.85 | 1.0938 | 0.061 | 9607.1976 | 6397.9875 | 1361.7 | 1752.1875 | 97.722 |  | 66.58% | 14.17% | 18.23% | 1.017% | 100%
System Capacity Demand (FY13 Actual) | 21.3882 | 10.7906 | 2.1125 | 7.7437 | 0.732 | 34255.4212 | 17286.5812 | 3384.225 | 12405.4875 | 1172.664 |  | 50.45% | 9.877% | 36.21% | 3.422% | 99.96%
118.8%
Deficit Hours by role
System Projects - Headcount Deficit/Surplus |  | -1.7265 | -0.338 | -1.239 | -0.11712

## REF (hidden)
Team | Project Status | Stage | Stage Name | Task Name | Resource locked | Task code | Hours required typically | Project code | 0 | 1.0001 | 1.0001 | SALES | TEAM | PM |  | ACTIVE | 1 | PMO | CasinoLink | FY14 | Week# | wk# | PERIOD | WK start | wk start (Monday) | WK end | MONTH | PERIOD | wk# | WE | month | Baseline
1 | ACTIVE | 1 | Initiation | Initiating | PM | 100 |  | 1100 | 1 | 1.001 | 1.001 | Elvio Beautemps | 1 | Elvio Beautemps | 1.001 | CONFIRMED | 2 | PMO | Advantage | 2013-09-29 | 1 | 1 | 1 | 2013-09-29 | 2013-09-30 | 2013-10-05 | OCT | 1 | 1 | 2013-10-05
1 | ACTIVE | 2 | Planning | Project Charter | PM | 200 |  | 1200 | 2 | 1.002 | 1.002 | Norberto Acevedo | 2 | Norberto Acevedo | 1.002 | BACKLOG | 3 | PMO | SBX | 2013-09-30 | 1 | 2 | 1 | 2013-10-06 | 2013-10-07 | 2013-10-12 | OCT | 1 | 2 | 2013-10-12
1 | ACTIVE | 2 | Planning | Project Plan | PM | 201 |  | 1201 | 3 | 1.003 | 1.003 | Gustavo Schleider | 3 | Gustavo Schleider | 1.003 | REQUEST | 4 | PS | Cloud | 2013-10-01 | 1 | 3 | 1 | 2013-10-13 | 2013-10-14 | 2013-10-19 | OCT | 1 | 3 | 2013-10-19
1 | ACTIVE | 2 | Planning | Procurement of parts | PM | 202 |  | 1202 | 4 | 1.004 | 1.004 | U.S. Cloud | 0 | SALES | 1.0001 | HOLD | 5 | PS | EZPay | 2013-10-02 | 1 | 4 | 1 | 2013-10-20 | 2013-10-21 | 2013-10-26 | OCT | 1 | 4 | 2013-10-26
1 | ACTIVE | 2 | Planning | Procurement of parts | SA | 203 |  | 1203 | 5 | 1.005 | 1.005 | NA |  |  |  | COMPLETED | 6 | AR | Interactive | 2013-10-03 | 1 | 5 | 2 | 2013-10-27 | 2013-10-28 | 2013-11-02 | NOV | 2 | 5 | 2013-11-02
1 | ACTIVE | 2 | Planning | Monitor progress & contract signature | PM | 204 |  | 1204 | 6 | 1.006 | 1.006 | NA |  |  |  | CANCELLED | 7 | na | TITO | 2013-10-04 | 1 | 6 | 2 | 2013-11-03 | 2013-11-04 | 2013-11-09 | NOV | 2 | 6 | 2013-11-09
1 | ACTIVE | 3 | Execution | PM | PM | 300 |  | 1300 | 7 | 1.007 | 1.007 | NA |  |  |  | other | na |  | UGA | 2013-10-05 | 1 | 7 | 2 | 2013-11-10 | 2013-11-11 | 2013-11-16 | NOV | 2 | 7 | 2013-11-16
1 | ACTIVE | 3 | Execution | SE | SE | 301 |  | 1301 | 8 | 1.008 | 1.008 | [7 empty] | Support | 2013-10-06 | 2 | 8 | 2 | 2013-11-17 | 2013-11-18 | 2013-11-23 | NOV | 2 | 8 | 2013-11-23
1 | ACTIVE | 3 | Execution | TRN | TRN | 302 |  | 1302 | 9 | 1.009 | 1.009 | [7 empty] | Managed Services | 2013-10-07 | 2 | 9 | 3 | 2013-11-24 | 2013-11-25 | 2013-11-30 | DEC | 3 | 9 | 2013-11-30
1 | ACTIVE | 4 | GoLive | PM | PM | 400 |  | 1400 | 10 | 1.01 | 1.01 | [7 empty] | needs update | 2013-10-08 | 2 | 10 | 3 | 2013-12-01 | 2013-12-02 | 2013-12-07 | DEC | 3 | 10 | 2013-12-07
1 | ACTIVE | 4 | GoLive | SE | SE | 401 |  | 1401 | 11 |  | 0 | [8 empty] | 2013-10-09 | 2 | 11 | 3 | 2013-12-08 | 2013-12-09 | 2013-12-14 | DEC | 3 | 11 | 2013-12-14
1 | ACTIVE | 4 | GoLive | TRN | TRN | 402 |  | 1402 | 12 |  | 0 | [8 empty] | 2013-10-10 | 2 | 12 | 3 | 2013-12-15 | 2013-12-16 | 2013-12-21 | DEC | 3 | 12 | 2013-12-21
1 | ACTIVE | 5 | Closing | PM | PM | 500 |  | 1500 | 13 |  | 0 | [8 empty] | 2013-10-11 | 2 | 13 | 3 | 2013-12-22 | 2013-12-23 | 2013-12-28 | DEC | 3 | 13 | 2013-12-28
2 | ACTIVE | 1 | Initiation | Initiating | PM | 100 |  | 2100 | 14 |  | 0 | [8 empty] | 2013-10-12 | 2 | 14 | 4 | 2013-12-29 | 2013-12-30 | 2014-01-04 | JAN | 4 | 14 | 2014-01-04
2 | ACTIVE | 2 | Planning | Project Charter | PM | 200 |  | 2200 | 15 |  | 0 | [8 empty] | 2013-10-13 | 3 | 15 | 4 | 2014-01-05 | 2014-01-06 | 2014-01-11 | JAN | 4 | 15 | 2014-01-11
2 | ACTIVE | 2 | Planning | Project Plan | PM | 201 |  | 2201 | 16 |  | 0 | [8 empty] | 2013-10-14 | 3 | 16 | 4 | 2014-01-12 | 2014-01-13 | 2014-01-18 | JAN | 4 | 16 | 2014-01-18
2 | ACTIVE | 2 | Planning | Procurement of parts | PM | 202 |  | 2202 | 17 |  | 0 | [8 empty] | 2013-10-15 | 3 | 17 | 4 | 2014-01-19 | 2014-01-20 | 2014-01-25 | JAN | 4 | 17 | 2014-01-25
2 | ACTIVE | 2 | Planning | Procurement of parts | SA | 203 |  | 2203 | 18 |  | 0 | [8 empty] | 2013-10-16 | 3 | 18 | 5 | 2014-01-26 | 2014-01-27 | 2014-02-01 | FEB | 5 | 18 | 2014-02-01
2 | ACTIVE | 2 | Planning | Monitor progress & contract signature | PM | 204 |  | 2204 | 19 |  | 0 | [8 empty] | 2013-10-17 | 3 | 19 | 5 | 2014-02-02 | 2014-02-03 | 2014-02-08 | FEB |  | 19 | 2014-02-08
2 | ACTIVE | 3 | Execution | PM | PM | 300 |  | 2300 | 20 |  | 0 | [8 empty] | 2013-10-18 | 3 | 20 | 5 | 2014-02-09 | 2014-02-10 | 2014-02-15 | FEB | 5 | 20 | 2014-02-15
2 | ACTIVE | 3 | Execution | SE | SE | 301 |  | 2301 |  |  | 0 | [8 empty] | 2013-10-19 | 3 | 21 | 5 | 2014-02-16 | 2014-02-17 | 2014-02-22 | FEB | 5 | 21 | 2014-02-22
2 | ACTIVE | 3 | Execution | TRN | TRN | 302 |  | 2302 |  |  | 0 | [8 empty] | 2013-10-20 | 4 | 22 | 6 | 2014-02-23 | 2014-02-24 | 2014-03-01 | MAR | 6 | 22 | 2014-03-01
2 | ACTIVE | 4 | GoLive | PM | PM | 400 |  | 2400 |  |  | 0 | [8 empty] | 2013-10-21 | 4 | 23 | 6 | 2014-03-02 | 2014-03-03 | 2014-03-08 | MAR | 6 | 23 | 2014-03-08
2 | ACTIVE | 4 | GoLive | SE | SE | 401 |  | 2401 | [11 empty] | 2013-10-22 | 4 | 24 | 6 | 2014-03-09 | 2014-03-10 | 2014-03-15 | MAR | 6 | 24 | 2014-03-15
2 | ACTIVE | 4 | GoLive | TRN | TRN | 402 |  | 2402 | [11 empty] | 2013-10-23 | 4 | 25 | 6 | 2014-03-16 | 2014-03-17 | 2014-03-22 | MAR | 6 | 25 | 2014-03-22
2 | ACTIVE | 5 | Closing | PM | PM | 500 |  | 2500 | [11 empty] | 2013-10-24 | 4 | 26 | 6 | 2014-03-23 | 2014-03-24 | 2014-03-29 | MAR | 6 | 26 | 2014-03-29
3 | ACTIVE | 1 | Initiation | Initiating | PM | 100 |  | 3100 | [11 empty] | 2013-10-25 | 4 | 27 | 7 | 2014-03-30 | 2014-03-31 | 2014-04-05 | APR | 7 | 27 | 2014-04-05
3 | ACTIVE | 2 | Planning | Project Charter | PM | 200 |  | 3200 | [11 empty] | 2013-10-26 | 4 | 28 | 7 | 2014-04-06 | 2014-04-07 | 2014-04-12 | APR | 7 | 28 | 2014-04-12
3 | ACTIVE | 2 | Planning | Project Plan | PM | 201 |  | 3201 | [11 empty] | 2013-10-27 | 5 | 29 | 7 | 2014-04-13 | 2014-04-14 | 2014-04-19 | APR | 7 | 29 | 2014-04-19
3 | ACTIVE | 2 | Planning | Procurement of parts | PM | 202 |  | 3202 | [11 empty] | 2013-10-28 | 5 | 30 | 7 | 2014-04-20 | 2014-04-21 | 2014-04-26 | APR | 7 | 30 | 2014-04-26
3 | ACTIVE | 2 | Planning | Procurement of parts | SA | 203 |  | 3203 | [11 empty] | 2013-10-29 | 5 | 31 | 8 | 2014-04-27 | 2014-04-28 | 2014-05-03 | MAY | 8 | 31 | 2014-05-03
3 | ACTIVE | 2 | Planning | Monitor progress & contract signature | PM | 204 |  | 3204 | [11 empty] | 2013-10-30 | 5 | 32 | 8 | 2014-05-04 | 2014-05-05 | 2014-05-10 | MAY | 8 | 32 | 2014-05-10
3 | ACTIVE | 3 | Execution | PM | PM | 300 |  | 3300 | [11 empty] | 2013-10-31 | 5 | 33 | 8 | 2014-05-11 | 2014-05-12 | 2014-05-17 | MAY | 8 | 33 | 2014-05-17
3 | ACTIVE | 3 | Execution | SE | SE | 301 |  | 3301 | [11 empty] | 2013-11-01 | 5 | 34 | 8 | 2014-05-18 | 2014-05-19 | 2014-05-24 | MAY | 8 | 34 | 2014-05-24
3 | ACTIVE | 3 | Execution | TRN | TRN | 302 |  | 3302 | [11 empty] | 2013-11-02 | 5 | 35 | 9 | 2014-05-25 | 2014-05-26 | 2014-05-31 | JUN | 9 | 35 | 2014-05-31
3 | ACTIVE | 4 | GoLive | PM | PM | 400 |  | 3400 | [11 empty] | 2013-11-03 | 6 | 36 | 9 | 2014-06-01 | 2014-06-02 | 2014-06-07 | JUN | 9 | 36 | 2014-06-07
3 | ACTIVE | 4 | GoLive | SE | SE | 401 |  | 3401 | [11 empty] | 2013-11-04 | 6 | 37 | 9 | 2014-06-08 | 2014-06-09 | 2014-06-14 | JUN | 9 | 37 | 2014-06-14
3 | ACTIVE | 4 | GoLive | TRN | TRN | 402 |  | 3402 | [11 empty] | 2013-11-05 | 6 | 38 | 9 | 2014-06-15 | 2014-06-16 | 2014-06-21 | JUN | 9 | 38 | 2014-06-21
3 | ACTIVE | 5 | Closing | PM | PM | 500 |  | 3500 | [11 empty] | 2013-11-06 | 6 | 39 | 9 | 2014-06-22 | 2014-06-23 | 2014-06-28 | JUN | 9 | 39 | 2014-06-28
0 | BACKLOG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 2013-11-07 | 6 | 40 | 10 | 2014-06-29 | 2014-06-30 | 2014-07-05 | JUL | 10 | 40 | 2014-07-05
0 | REQUEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 2013-11-08 | 6 | 41 | 10 | 2014-07-06 | 2014-07-07 | 2014-07-12 | JUL | 10 | 41 | 2014-07-12
0 | HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 2013-11-09 | 6 | 42 | 10 | 2014-07-13 | 2014-07-14 | 2014-07-19 | JUL | 10 | 42 | 2014-07-19
0 | PIPELINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 2013-11-10 | 7 | 43 | 10 | 2014-07-20 | 2014-07-21 | 2014-07-26 | JUL | 10 | 43 | 2014-07-26
0 | COMPLETED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 2013-11-11 | 7 | 44 | 11 | 2014-07-27 | 2014-07-28 | 2014-08-02 | AUG | 11 | 44 | 2014-08-02
0 | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 2013-11-12 | 7 | 45 | 11 | 2014-08-03 | 2014-08-04 | 2014-08-09 | AUG | 11 | 45 | 2014-08-09
[20 empty] | 2013-11-13 | 7 | 46 | 11 | 2014-08-10 | 2014-08-11 | 2014-08-16 | AUG | 11 | 46 | 2014-08-16
[20 empty] | 2013-11-14 | 7 | 47 | 11 | 2014-08-17 | 2014-08-18 | 2014-08-23 | AUG | 11 | 47 | 2014-08-23
[20 empty] | 2013-11-15 | 7 | 48 | 12 | 2014-08-24 | 2014-08-25 | 2014-08-30 | SEP | 12 | 48 | 2014-08-30
[20 empty] | 2013-11-16 | 7 | 49 | 12 | 2014-08-31 | 2014-09-01 | 2014-09-06 | SEP | 12 | 49 | 2014-09-06
[20 empty] | 2013-11-17 | 8 | 50 | 12 | 2014-09-07 | 2014-09-08 | 2014-09-13 | SEP | 12 | 50 | 2014-09-13
[20 empty] | 2013-11-18 | 8 | 51 | 12 | 2014-09-14 | 2014-09-15 | 2014-09-20 | SEP | 12 | 51 | 2014-09-20
[20 empty] | 2013-11-19 | 8 | 52 | 12 | 2014-09-21 | 2014-09-22 | 2014-09-27 | SEP | 12 | 52 | 2014-09-27
[20 empty] | 2013-11-20 | 8
[20 empty] | 2013-11-21 | 8
[20 empty] | 2013-11-22 | 8
[20 empty] | 2013-11-23 | 8
[20 empty] | 2013-11-24 | 9
[20 empty] | 2013-11-25 | 9
[20 empty] | 2013-11-26 | 9
[20 empty] | 2013-11-27 | 9
[20 empty] | 2013-11-28 | 9
[20 empty] | 2013-11-29 | 9
[20 empty] | 2013-11-30 | 9
[20 empty] | 2013-12-01 | 10
[20 empty] | 2013-12-02 | 10
[20 empty] | 2013-12-03 | 10
[20 empty] | 2013-12-04 | 10
[20 empty] | 2013-12-05 | 10
[20 empty] | 2013-12-06 | 10
[20 empty] | 2013-12-07 | 10
[20 empty] | 2013-12-08 | 11
[20 empty] | 2013-12-09 | 11
[20 empty] | 2013-12-10 | 11
[20 empty] | 2013-12-11 | 11
[20 empty] | 2013-12-12 | 11
[20 empty] | 2013-12-13 | 11
[20 empty] | 2013-12-14 | 11
[20 empty] | 2013-12-15 | 12
[20 empty] | 2013-12-16 | 12
[20 empty] | 2013-12-17 | 12
[20 empty] | 2013-12-18 | 12
[20 empty] | 2013-12-19 | 12
[20 empty] | 2013-12-20 | 12
[20 empty] | 2013-12-21 | 12
[20 empty] | 2013-12-22 | 13
[20 empty] | 2013-12-23 | 13
[20 empty] | 2013-12-24 | 13
[20 empty] | 2013-12-25 | 13
[20 empty] | 2013-12-26 | 13
[20 empty] | 2013-12-27 | 13
[20 empty] | 2013-12-28 | 13
[20 empty] | 2013-12-29 | 14
[20 empty] | 2013-12-30 | 14
[20 empty] | 2013-12-31 | 14
[20 empty] | 2014-01-01 | 14
[20 empty] | 2014-01-02 | 14
[20 empty] | 2014-01-03 | 14
[20 empty] | 2014-01-04 | 14
[20 empty] | 2014-01-05 | 15
[20 empty] | 2014-01-06 | 15
[20 empty] | 2014-01-07 | 15
[20 empty] | 2014-01-08 | 15
[20 empty] | 2014-01-09 | 15
[20 empty] | 2014-01-10 | 15
[20 empty] | 2014-01-11 | 15
[20 empty] | 2014-01-12 | 16
[20 empty] | 2014-01-13 | 16
[20 empty] | 2014-01-14 | 16
[20 empty] | 2014-01-15 | 16
[20 empty] | 2014-01-16 | 16
[20 empty] | 2014-01-17 | 16
[20 empty] | 2014-01-18 | 16
[20 empty] | 2014-01-19 | 17
[20 empty] | 2014-01-20 | 17
[20 empty] | 2014-01-21 | 17
[20 empty] | 2014-01-22 | 17
[20 empty] | 2014-01-23 | 17
[20 empty] | 2014-01-24 | 17
[20 empty] | 2014-01-25 | 17
[20 empty] | 2014-01-26 | 18
[20 empty] | 2014-01-27 | 18
[20 empty] | 2014-01-28 | 18
[20 empty] | 2014-01-29 | 18
[20 empty] | 2014-01-30 | 18
[20 empty] | 2014-01-31 | 18
[20 empty] | 2014-02-01 | 18
[20 empty] | 2014-02-02 | 19
[20 empty] | 2014-02-03 | 19
[20 empty] | 2014-02-04 | 19
[20 empty] | 2014-02-05 | 19
[20 empty] | 2014-02-06 | 19
[20 empty] | 2014-02-07 | 19
[20 empty] | 2014-02-08 | 19
[20 empty] | 2014-02-09 | 20
[20 empty] | 2014-02-10 | 20
[20 empty] | 2014-02-11 | 20
[20 empty] | 2014-02-12 | 20
[20 empty] | 2014-02-13 | 20
[20 empty] | 2014-02-14 | 20
[20 empty] | 2014-02-15 | 20
[20 empty] | 2014-02-16 | 21
[20 empty] | 2014-02-17 | 21
[20 empty] | 2014-02-18 | 21
[20 empty] | 2014-02-19 | 21
[20 empty] | 2014-02-20 | 21
[20 empty] | 2014-02-21 | 21
[20 empty] | 2014-02-22 | 21
[20 empty] | 2014-02-23 | 22
[20 empty] | 2014-02-24 | 22
[20 empty] | 2014-02-25 | 22
[20 empty] | 2014-02-26 | 22
[20 empty] | 2014-02-27 | 22
[20 empty] | 2014-02-28 | 22
[20 empty] | 2014-03-01 | 22
[20 empty] | 2014-03-02 | 23
[20 empty] | 2014-03-03 | 23
[20 empty] | 2014-03-04 | 23
[20 empty] | 2014-03-05 | 23
[20 empty] | 2014-03-06 | 23
[20 empty] | 2014-03-07 | 23
[20 empty] | 2014-03-08 | 23
[20 empty] | 2014-03-09 | 24
[20 empty] | 2014-03-10 | 24
[20 empty] | 2014-03-11 | 24
[20 empty] | 2014-03-12 | 24
[20 empty] | 2014-03-13 | 24
[20 empty] | 2014-03-14 | 24
[20 empty] | 2014-03-15 | 24
[20 empty] | 2014-03-16 | 25
[20 empty] | 2014-03-17 | 25
[20 empty] | 2014-03-18 | 25
[20 empty] | 2014-03-19 | 25
[20 empty] | 2014-03-20 | 25
[20 empty] | 2014-03-21 | 25
[20 empty] | 2014-03-22 | 25
[20 empty] | 2014-03-23 | 26
[20 empty] | 2014-03-24 | 26
[20 empty] | 2014-03-25 | 26
[20 empty] | 2014-03-26 | 26
[20 empty] | 2014-03-27 | 26
[20 empty] | 2014-03-28 | 26
[20 empty] | 2014-03-29 | 26
[20 empty] | 2014-03-30 | 27
[20 empty] | 2014-03-31 | 27
[20 empty] | 2014-04-01 | 27
[20 empty] | 2014-04-02 | 27
[20 empty] | 2014-04-03 | 27
[20 empty] | 2014-04-04 | 27
[20 empty] | 2014-04-05 | 27
[20 empty] | 2014-04-06 | 28
[20 empty] | 2014-04-07 | 28
[20 empty] | 2014-04-08 | 28
[20 empty] | 2014-04-09 | 28
[20 empty] | 2014-04-10 | 28
[20 empty] | 2014-04-11 | 28
[20 empty] | 2014-04-12 | 28
[20 empty] | 2014-04-13 | 29
[20 empty] | 2014-04-14 | 29
[20 empty] | 2014-04-15 | 29
[20 empty] | 2014-04-16 | 29
[20 empty] | 2014-04-17 | 29
[20 empty] | 2014-04-18 | 29
[20 empty] | 2014-04-19 | 29
[20 empty] | 2014-04-20 | 30
[20 empty] | 2014-04-21 | 30
[20 empty] | 2014-04-22 | 30
[20 empty] | 2014-04-23 | 30
[20 empty] | 2014-04-24 | 30
[20 empty] | 2014-04-25 | 30
[20 empty] | 2014-04-26 | 30
[20 empty] | 2014-04-27 | 31
[20 empty] | 2014-04-28 | 31
[20 empty] | 2014-04-29 | 31
[20 empty] | 2014-04-30 | 31
[20 empty] | 2014-05-01 | 31
[20 empty] | 2014-05-02 | 31
[20 empty] | 2014-05-03 | 31
[20 empty] | 2014-05-04 | 32
[20 empty] | 2014-05-05 | 32
[20 empty] | 2014-05-06 | 32
[20 empty] | 2014-05-07 | 32
[20 empty] | 2014-05-08 | 32
[20 empty] | 2014-05-09 | 32
[20 empty] | 2014-05-10 | 32
[20 empty] | 2014-05-11 | 33
[20 empty] | 2014-05-12 | 33
[20 empty] | 2014-05-13 | 33
[20 empty] | 2014-05-14 | 33
[20 empty] | 2014-05-15 | 33
[20 empty] | 2014-05-16 | 33
[20 empty] | 2014-05-17 | 33
[20 empty] | 2014-05-18 | 34
[20 empty] | 2014-05-19 | 34
[20 empty] | 2014-05-20 | 34
[20 empty] | 2014-05-21 | 34
[20 empty] | 2014-05-22 | 34
[20 empty] | 2014-05-23 | 34
[20 empty] | 2014-05-24 | 34
[20 empty] | 2014-05-25 | 35
[20 empty] | 2014-05-26 | 35
[20 empty] | 2014-05-27 | 35
[20 empty] | 2014-05-28 | 35
[20 empty] | 2014-05-29 | 35
[20 empty] | 2014-05-30 | 35
[20 empty] | 2014-05-31 | 35
[20 empty] | 2014-06-01 | 36
[20 empty] | 2014-06-02 | 36
[20 empty] | 2014-06-03 | 36
[20 empty] | 2014-06-04 | 36
[20 empty] | 2014-06-05 | 36
[20 empty] | 2014-06-06 | 36
[20 empty] | 2014-06-07 | 36
[20 empty] | 2014-06-08 | 37
[20 empty] | 2014-06-09 | 37
[20 empty] | 2014-06-10 | 37
[20 empty] | 2014-06-11 | 37
[20 empty] | 2014-06-12 | 37
[20 empty] | 2014-06-13 | 37
[20 empty] | 2014-06-14 | 37
[20 empty] | 2014-06-15 | 38
[20 empty] | 2014-06-16 | 38
[20 empty] | 2014-06-17 | 38
[20 empty] | 2014-06-18 | 38
[20 empty] | 2014-06-19 | 38
[20 empty] | 2014-06-20 | 38
[20 empty] | 2014-06-21 | 38
[20 empty] | 2014-06-22 | 39
[20 empty] | 2014-06-23 | 39
[20 empty] | 2014-06-24 | 39
[20 empty] | 2014-06-25 | 39
[20 empty] | 2014-06-26 | 39
[20 empty] | 2014-06-27 | 39
[20 empty] | 2014-06-28 | 39
[20 empty] | 2014-06-29 | 40
[20 empty] | 2014-06-30 | 40
[20 empty] | 2014-07-01 | 40
[20 empty] | 2014-07-02 | 40
[20 empty] | 2014-07-03 | 40
[20 empty] | 2014-07-04 | 40
[20 empty] | 2014-07-05 | 40
[20 empty] | 2014-07-06 | 41
[20 empty] | 2014-07-07 | 41
[20 empty] | 2014-07-08 | 41
[20 empty] | 2014-07-09 | 41
[20 empty] | 2014-07-10 | 41
[20 empty] | 2014-07-11 | 41
[20 empty] | 2014-07-12 | 41
[20 empty] | 2014-07-13 | 42
[20 empty] | 2014-07-14 | 42
[20 empty] | 2014-07-15 | 42
[20 empty] | 2014-07-16 | 42
[20 empty] | 2014-07-17 | 42
[20 empty] | 2014-07-18 | 42
[20 empty] | 2014-07-19 | 42
[20 empty] | 2014-07-20 | 43
[20 empty] | 2014-07-21 | 43
[20 empty] | 2014-07-22 | 43
[20 empty] | 2014-07-23 | 43
[20 empty] | 2014-07-24 | 43
[20 empty] | 2014-07-25 | 43
[20 empty] | 2014-07-26 | 43
[20 empty] | 2014-07-27 | 44
[20 empty] | 2014-07-28 | 44
[20 empty] | 2014-07-29 | 44
[20 empty] | 2014-07-30 | 44
[20 empty] | 2014-07-31 | 44
[20 empty] | 2014-08-01 | 44
[20 empty] | 2014-08-02 | 44
[20 empty] | 2014-08-03 | 45
[20 empty] | 2014-08-04 | 45
[20 empty] | 2014-08-05 | 45
[20 empty] | 2014-08-06 | 45
[20 empty] | 2014-08-07 | 45
[20 empty] | 2014-08-08 | 45
[20 empty] | 2014-08-09 | 45
[20 empty] | 2014-08-10 | 46
[20 empty] | 2014-08-11 | 46
[20 empty] | 2014-08-12 | 46
[20 empty] | 2014-08-13 | 46
[20 empty] | 2014-08-14 | 46
[20 empty] | 2014-08-15 | 46
[20 empty] | 2014-08-16 | 46
[20 empty] | 2014-08-17 | 47
[20 empty] | 2014-08-18 | 47
[20 empty] | 2014-08-19 | 47
[20 empty] | 2014-08-20 | 47
[20 empty] | 2014-08-21 | 47
[20 empty] | 2014-08-22 | 47
[20 empty] | 2014-08-23 | 47
[20 empty] | 2014-08-24 | 48
[20 empty] | 2014-08-25 | 48
[20 empty] | 2014-08-26 | 48
[20 empty] | 2014-08-27 | 48
[20 empty] | 2014-08-28 | 48
[20 empty] | 2014-08-29 | 48
[20 empty] | 2014-08-30 | 48
[20 empty] | 2014-08-31 | 49
[20 empty] | 2014-09-01 | 49
[20 empty] | 2014-09-02 | 49
[20 empty] | 2014-09-03 | 49
[20 empty] | 2014-09-04 | 49
[20 empty] | 2014-09-05 | 49
[20 empty] | 2014-09-06 | 49
[20 empty] | 2014-09-07 | 50
[20 empty] | 2014-09-08 | 50
[20 empty] | 2014-09-09 | 50
[20 empty] | 2014-09-10 | 50
[20 empty] | 2014-09-11 | 50
[20 empty] | 2014-09-12 | 50
[20 empty] | 2014-09-13 | 50
[20 empty] | 2014-09-14 | 51
[20 empty] | 2014-09-15 | 51
[20 empty] | 2014-09-16 | 51
[20 empty] | 2014-09-17 | 51
[20 empty] | 2014-09-18 | 51
[20 empty] | 2014-09-19 | 51
[20 empty] | 2014-09-20 | 51
[20 empty] | 2014-09-21 | 52
[20 empty] | 2014-09-22 | 52
[20 empty] | 2014-09-23 | 52
[20 empty] | 2014-09-24 | 52
[20 empty] | 2014-09-25 | 52
[20 empty] | 2014-09-26 | 52
[20 empty] | 2014-09-27 | 52
Stage data validation
Product

## Project Assignment (hours) (hidden)
2020-01-24 | [50 empty] | wk start | 2013-09-29 | 2013-10-06 | 2013-10-13 | 2013-10-20 | 2013-10-27 | 2013-11-03 | 2013-11-10 | 2013-11-17 | 2013-11-24 | 2013-12-01 | 2013-12-08 | 2013-12-15 | 2013-12-22 | 2013-12-29 | 2014-01-05 | 2014-01-12 | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02 | 2014-03-09 | 2014-03-16 | 2014-03-23 | 2014-03-30 | 2014-04-06 | 2014-04-13 | 2014-04-20 | 2014-04-27 | 2014-05-04 | 2014-05-11 | 2014-05-18 | 2014-05-25 | 2014-06-01 | 2014-06-08 | 2014-06-15 | 2014-06-22 | 2014-06-29 | 2014-07-06 | 2014-07-13 | 2014-07-20 | 2014-07-27 | 2014-08-03 | 2014-08-10 | 2014-08-17 | 2014-08-24 | 2014-08-31 | 2014-09-07 | 2014-09-14 | 2014-09-21
#N/A | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | month | October (P1 FY14) |  |  |  | November (P2 FY14) |  |  |  | December (P3 FY14) |  |  |  |  | January (P4 FY14) |  |  |  | February (P5 FY14) |  |  |  | March (P6 FY14) |  |  |  |  | April (P7 FY14) |  |  |  | May (P8 FY14) |  |  |  | June (P9 FY14) |  |  |  |  | July (P10 FY14) |  |  |  | August (P11 FY14) |  |  |  | September (P12 FY14)
[51 empty] | WE | 2013-10-05 | 2013-10-12 | 2013-10-19 | 2013-10-26 | 2013-11-02 | 2013-11-09 | 2013-11-16 | 2013-11-23 | 2013-11-30 | 2013-12-07 | 2013-12-14 | 2013-12-21 | 2013-12-28 | 2014-01-04 | 2014-01-11 | 2014-01-18 | 2014-01-25 | 2014-02-01 | 2014-02-08 | 2014-02-15 | 2014-02-22 | 2014-03-01 | 2014-03-08 | 2014-03-15 | 2014-03-22 | 2014-03-29 | 2014-04-05 | 2014-04-12 | 2014-04-19 | 2014-04-26 | 2014-05-03 | 2014-05-10 | 2014-05-17 | 2014-05-24 | 2014-05-31 | 2014-06-07 | 2014-06-14 | 2014-06-21 | 2014-06-28 | 2014-07-05 | 2014-07-12 | 2014-07-19 | 2014-07-26 | 2014-08-02 | 2014-08-09 | 2014-08-16 | 2014-08-23 | 2014-08-30 | 2014-09-06 | 2014-09-13 | 2014-09-20 | 2014-09-27
| Resources - System projects | [7 empty] | DEC | DEC | JAN | JAN | JAN | JAN | FEB | FEB | FEB | FEB | MAR | MAR | MAR | MAR | MAR | APR | APR | APR | APR | MAY | MAY | MAY | MAY | JUN | JUN | JUN | JUN | JUN | JUL | JUL | JUL | JUL | AUG | AUG | AUG | AUG | SEP | SEP | SEP | SEP | SEP |  | we# | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
TEAM | ROLE | NAME | BASE COUNTRY | REGION | project assigned | Avail Weeks | Avail Hours | Assingned Hours | 2013-12-16 | 2013-12-23 | 2013-12-30 | 2014-01-06 | 2014-01-13 | 2014-01-20 | 2014-01-27 | 2014-02-03 | 2014-02-10 | 2014-02-17 | 2014-02-24 | 2014-03-03 | 2014-03-10 | 2014-03-17 | 2014-03-24 | 2014-03-31 | 2014-04-07 | 2014-04-14 | 2014-04-21 | 2014-04-28 | 2014-05-05 | 2014-05-12 | 2014-05-19 | 2014-05-26 | 2014-06-02 | 2014-06-09 | 2014-06-16 | 2014-06-23 | 2014-06-30 | 2014-07-07 | 2014-07-14 | 2014-07-21 | 2014-07-28 | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | FY14 | wk start (MONDAY) | time axis 2013-09-30 to 2014-09-22
1 | PM | Elvio Beautemps | Argentina | SOLA | 1 | 12.8 | 512 | 128 |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 16 | 40 | 40 | 16 | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PM | Juan Di Feo | Argentina | SOLA | 2 | 13.95 | 558 | 82 | [9 empty] | 32 | 8 | 16 | 16 | 1 | 1 | 8 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PM | OPEN | OPEN | OPEN | 3 | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Martin Kutter | Argentina | SOLA | ? | 12.8 | 512 | 128 | [12 empty] | 40 | 40 | 20 | 20 | 8 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Pablo Amarfil | Argentina | SOLA |  | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Emanuel Dafonte | Argentina | SOLA | 2 | 13.1 | 524 | 116 | [9 empty] | 40 | 4 | 24 | 24 |  |  | 24 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Bernardo Brauning | Argentina | SOLA |  | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Emilio Pagano | Argentina | SOLA | support | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Mario Rendon | MEXICO | MEXICO |  | 11.4 | 456 | 184 | 24 |  |  | 24 | 24 | 24 | 24 | 24 | 24 | 40 | 24 | 40 | 40 | 16 | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Juan Pablo Maya | MEXICO | MEXICO | ? | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Oscar Gomez | MEXICO | MEXICO | support | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Kayode Showunmi | MEXICO | MEXICO | support | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SE | Luigi Provacia | ARUBA | MCLAC | support | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Trainer | Katie Katayose | U.S. | MCLAC | 1.2 | 10.1 | 404 | 236 |  |  |  | 5 | 5 | 5 | 16 | 16 | 16 | 32 | 20 | 64 | 64 | 16 |  | 24 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Trainer | Roxana Di Franco | Argentina | SOLA | 2 | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Trainer | Dion Pom | ARUBA | MCLAC | 0 | 16 | 640 | 0 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 (CET PM) | Manager | Gustavo Schleider | Argentina | SOLA | 4 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 (CET PM) | AM | Fernando Pagani (acting as PM - SE needed; prep work already done) | Argentina | SOLA | 5 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | up to 8 hrs | [49 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 9 - 23 | [49 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 24 - 32 | [49 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | >32 | [49 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CURRENT PROJECTS: | [5 empty] | Project start | Completion date
Project-1 | CasinoLink | Star Bay Casino (Ice Gaming Corporation) | Star Bay Casino (Latin Gaming) - Casino Link |  |  | 2014-02-17 | 2014-05-16
Project-2 | Golden Gaming S.A. (Golden Palace) | Bonusing Samcorp Lab – Golden Palace – La Hacienda - Newport |  |  |  | 2014-02-17 | 2014-03-31
TECH | SBX-GOLDEN INVESTEMENT | ask Chris for tech with experience sbX (1. 2.) |  |  |  | 2014-03-14 | 2014-03-18
SE | SBX-GOLDEN INVESTEMENT | 1. Oscar Gomez, 2. Katode(MARIO RENDON) |  |  |  | 2014-03-17 | 2014-03-21
SE | SBX-GOLDEN INVESTEMENT | 1. Oscar Gomez, 2. Katode(MARIO RENDON) |  |  |  | 2014-03-24 | 2014-03-28
SE | SBX-GOLDEN INVESTEMENT | 1. Oscar Gomez, 2. Katode(MARIO RENDON) |  |  |  | 2014-04-16 | 2014-04-15
TRN | SBX-GOLDEN INVESTEMENT | EDGAR TREJO |  |  |  | 2014-04-17 | 2014-04-25
| Resources - EGM projects | [5 empty] | 40 wks (77%)
| PM | Horacio Garcia |  |  |  |  | 1601.6
| PM | Javier Rios |  |  |  |  | 1601.6
| Trainer | Domingo Rivera |  |  |  |  | 1601.6
| Trainer | Gersay Vasquez |  |  |  |  | 1601.6
| Trainer | Edgar Trejo |  |  |  |  | 1601.6
| Tech/PM | Cristian Totaro |  |  |  |  | 1601.6
| Supervisor | Mariano Cervino |  |  |  |  | 1601.6
| Supervisor | Isaias Soria |  |  |  |  | 1601.6
| Tech | Rafael Serrano |  |  |  |  | 1601.6
| Tech | Takir Méndez Gómez |  |  |  |  | 1601.6
| Tech | Wilson Rodriguez |  |  |  |  | 1601.6
| Tech | Reinaldo Berrios |  |  |  |  | 1601.6
| Tech | Félix Emil Díaz | PANAMA | MCLAC | 1 |  | 1601.6 | [10 empty] | 40 |  | 40 | 40 | 16
| Tech | Horacio Castilleja |  |  |  |  | 1601.6
| Tech | Isaac Martinez |  |  |  |  | 1601.6
| Tech | Mariano Perez Cobas |  |  |  |  | 1601.6
| Tech | Pablo Mercuri |  |  |  |  | 1601.6
| Tech | Facundo Gerez |  |  |  |  | 1601.6
| Tech | Tomas Hernandez |  |  |  |  | 1601.6
| Tech | Nestor Bordigoni |  |  |  |  | 1601.6
| Tech | Alejandro Mauricio Andreoli |  |  |  |  | 1601.6
| Tech | Santiago Bercovich |  |  |  |  | 1601.6
| Tech | Leandro Althabe |  |  |  |  | 1601.6
| Tech | Juan Ignacio Popolo |  |  |  |  | 1601.6
| Tech | Gustavo Javier Moreira |  |  |  |  | 1601.6
| Tech | Marco Cortes |  |  |  |  | 1601.6
| Tech | Oscar Meza |  |  |  |  | 1601.6
| Tech | Gerardo Martínez |  |  |  |  | 1601.6
| Tech | Ernesto Maurin |  |  |  |  | 1601.6
| Tech | Josué Heredia |  |  |  |  | 1601.6
| Tech | Roberto Sandoval |  |  |  |  | 1601.6
| Tech | Jairo Murillo |  |  |  |  | 1601.6
| Tech | Jorge Aparicio |  |  |  |  | 1601.6
| Tech | Ivan Gómez |  |  |  |  | 1601.6
| Tech | Luis Osuna |  |  |  |  | 1601.6
| Tech | Jaime Domínguez |  |  |  |  | 1601.6
| Tech | Jaime May |  |  |  |  | 1601.6
| Tech | Angel Godoy |  |  |  |  | 1601.6
| Tech | Francisco Vásquez |  |  |  |  | 1601.6
| Tech | Miguel Guzmán |  |  |  |  | 1601.6
| Tech | Alejandro Castillo |  |  |  |  | 1601.6
| Tech | Luis Pérez |  |  |  |  | 1601.6
| Tech | Cesar Montero |  |  |  |  | 1601.6
| Tech | Irving Morales |  |  |  |  | 1601.6
| Tech | Agustín Hernández |  |  |  |  | 1601.6
| Tech | Oscar Garcia |  |  |  |  | 1601.6
| Tech | Hugo Rodríguez |  |  |  |  | 1601.6
| Tech | Alejandro Guevara |  |  |  |  | 1601.6
| Tech | Alfredo Chávez |  |  |  |  | 1601.6
| Tech | Juan Manuel Castillo |  |  |  |  | 1601.6
80080
Elvio
Juan
Open
Calculation based on next 16 weeks assingments
16-week resource projects assignment (640 hrs)
Note on U19: schedule conflict: ***Katie required to be at two different sites!!!****
Note on V19: schdule conflict: ***Katie required to be at two different sites!!!****

## GlobalServicesOpportunities-Won (hidden)
[9 empty] | 57 | [5 empty] | 51015.32
Opportunity Owner | Opp Num | Opportunity Name | Account Name | Stage | Forecast Category | Probability (%) | Product Family | Product Name | Machine Qty | Monthly Quantity | Monthly Quantity | Close Date | Install Date | Monthly Amount Currency | Monthly Amount | Revenue Model | Region
Katty Lopez | OPP62945 | GG-Peru-Bonusing 388 | Golden Gaming S.A. | Closed Won | Closed | 100 | Global Services | Integration Services Install | 0 | 777 | 1 | 2014-01-17 | 2014-03-10 | USD | 13706.66 | Trade Sales | MCLAC
Fernando Pagani | OPP66700 | Bonusing 870 XC y PP | Golden Investment S.A. | Closed Won | Closed | 100 | Global Services | Integration Services Custom | 0 | 1741 | 1 | 2014-01-17 | 2014-03-03 | USD | 16106.66 | Trade Sales | MCLAC
Celene Sierra | OPP69265 | Sheraton Convention/2Conv | Sheraton Puerto Rico Convention | Closed Won | Closed | 100 | Global Services | Field Services - Install | 0 | 4 | 2 | 2014-01-10 | 2014-02-14 | USD | 400 | Trade Sales | MCLAC
Celene Sierra | OPP69403 | Maunaloa/IPC | Cool Casino | Closed Won | Closed | 100 | Global Services | Field Services - Install | 0 | 5 | 4 | 2014-01-16 | 2014-02-14 | USD | 800 | Trade Sales | MCLAC
Natalia Torres | OPP53334 | Cloud Rivera | Casino Rivera | Closed Won | Closed | 100 | Global Services | Field Services - Install | 0 | 27 | 1 | 2014-01-27 | 2014-04-01 | USD | 0 | Trade Sales | SOLA
Natalia Torres | OPP53334 | Cloud Rivera | Casino Rivera | Closed Won | Closed | 100 | Global Services | Integration Services Install | 0 | 27 | 1 | 2014-01-27 | 2014-04-01 | USD | 1 | Trade Sales | SOLA
Leonardo Sosa | OPP63801 | LRF Group - 5 machines | LRF Group S.A. | Closed Won | Closed | 100 | Global Services | Field Services - Install | 5 | 6 | 1 | 2014-02-07 | 2014-02-18 | USD | 0 | Trade Sales | SOLA
Fernando Pagani | OPP70115 | Cloud Rivera Esparcimiento | Sala de Esparcimiento | Closed Won | Closed | 100 | Global Services | Field Services - Install | 0 | 27 | 1 | 2014-01-27 | 2014-04-01 | USD | 0 | Trade Sales | SOLA
Fernando Pagani | OPP70115 | Cloud Rivera Esparcimiento | Sala de Esparcimiento | Closed Won | Closed | 100 | Global Services | Integration Services Install | 0 | 27 | 1 | 2014-01-27 | 2014-04-01 | USD | 1 | Trade Sales | SOLA
Marisol Sanchez | OPP63814 | Operadora Class Cloud Mtey Viva Mexico | Operadora Class S de RL de CV | Closed Won | Closed | 100 | Global Services | Integration Services | 0 | 21 | 1 | 2014-01-17 | 2014-01-31 | USD | 10000 | Trade Sales | Mexico
Marisol Sanchez | OPP63816 | Operadora Class Cloud Mtey New York | Operadora Class S de RL de CV | Closed Won | Closed | 100 | Global Services | Integration Services | 0 | 21 | 1 | 2014-01-06 | 2014-01-16 | USD | 10000 | Trade Sales | Mexico
Emilio Herrera Valdespino | OPP66394 | 8 Huevo Cartoon Daimonds Merida | Shalom Vehatzlaja Raba SA de CV | Closed Won | Closed | 100 | Global Services | Field Services - Install | 8 | 9 | 1 | 2014-01-24 | 2014-02-07 | USD | 0 | Trade Sales | Mexico
Emilio Herrera Valdespino | OPP66397 | 8 huevo Cartoon Winpot Cd del Carmen | Shalom Vehatzlaja Raba SA de CV | Closed Won | Closed | 100 | Global Services | Field Services - Install | 8 | 10 | 1 | 2014-01-20 | 2014-02-07 | USD | 0 | Trade Sales | Mexico
Emilio Herrera Valdespino | OPP66397 | 8 huevo Cartoon Winpot Cd del Carmen | Shalom Vehatzlaja Raba SA de CV | Closed Won | Closed | 100 | Global Services | Education Services | 8 | 10 | 1 | 2014-01-20 | 2014-02-07 | USD | 0 | Trade Sales | Mexico
Emilio Herrera Valdespino | OPP66399 | 8 Huevo Cartoon La paz | Shalom Vehatzlaja Raba SA de CV | Closed Won | Closed | 100 | Global Services | Field Services - Install | 8 | 10 | 1 | 2014-01-20 | 2014-02-28 | USD | 0 | Trade Sales | Mexico
Emilio Herrera Valdespino | OPP66399 | 8 Huevo Cartoon La paz | Shalom Vehatzlaja Raba SA de CV | Closed Won | Closed | 100 | Global Services | Education Technical Training Services | 8 | 10 | 1 | 2014-01-20 | 2014-02-28 | USD | 0 | Trade Sales | Mexico
Marisol Sanchez | OPP69398 | Operadora Class 6 G23LCD/Cloud Viva Mexico | Operadora Class S de RL de CV | Closed Won | Closed | 100 | Global Services | Field Services - Install | 6 | 13 | 6 | 2014-01-08 | 2014-01-31 | USD | 0 | Trade Sales | Mexico
Marisol Sanchez | OPP69398 | Operadora Class 6 G23LCD/Cloud Viva Mexico | Operadora Class S de RL de CV | Closed Won | Closed | 100 | Global Services | Education Technical Training Services | 6 | 13 | 1 | 2014-01-08 | 2014-01-31 | USD | 0 | Trade Sales | Mexico

## EGM Supply & Demand Analysis (hidden)
|  | AVAILABLE CAPACITY (goal) | [5 empty] | 100% | AVAILABLE HOURS/YEAR | 2080 | 77% | 23%
| Headcount | Available Hours | [5 empty] | Techs | 41 | 85280 | 65665.6 | 19614.4
| Avail. resouces | Total | Installations | Field service | Prevent-maint. | Special Projects (Systems) | Admin | PMs | 1 | 2080 | 1601.6 | 478.4
|  | 100% | 9% | 64% | 15% | 12% | 23% | Trainers | 1 | 2080 | 1601.6 | 478.4
TECHS | 41 | 85280 | 7675.2 | 54579.2 | 12792 | 10233.6 | 19614.4 |  | 43 | 89440 | 68868.8 | 20571.2
PM | 1 | 2080 | 0 |  |  | 520 | 478.4 | Labor allocation by activity |  |  | Optimum allocation (Otto) | Demand (SAP)
Trainers | 1 | 2080
EGM Capacity Supply | 43 | 89440 | 7675.2 | 54579.2 | 12792 | 10753.6 | 20092.8 | Installations |  |  | 9% | 9%
Current Available FS Supply |  | 43 | 3.69 | 26.24 | 6.15 | 5.17 | 41.25 | Field Service |  |  | 64% | 56%
[8 empty] | Preventive Maint |  |  | 15% | 4%
[8 empty] | Rework |  |  |  | 1%
[8 empty] | Interdepartmental |  |  |  | 1%
[8 empty] | Special Projects |  |  | 12% | 16%
|  | CAPACITY DEMAND - SAP FY13 Actual | [9 empty] | 13%
| Headcount | Actuals | [9 empty] | 100%
| Resource demand | Total | Installations | Field service | Prevent-maint. | Special Projects (Systems) | Admin
|  | 75.3% | 6.811% | 53.61% | 2.848% | 12.03% |  | 476.6667
TECHS | 41 | 65707.28 | 4648 | 47951.28 | 2547.2 | 10560.8
PM | 1 | 1644 | 1444 | 0 | 0 | 200
1
EGM Capacity Demand (FY13 Actual) | 43 | 67351.28 | 6092 | 47951.28 | 2547.2 | 10760.8 | 0
FS Capacity Demand - SAP Actual |  | 32.3804 | 2.9288 | 23.0535 | 1.2246 | 5.1735
FS - Headcount Deficit/Surplus |  | 10.6196 | 0.76115 | 3.1865 | 4.9254 | -0.0034615
| Headcount conversion | 32.3804 | 2.9288 | 23.0535 | 1.2246 | 5.1735 | 32.3804
|  | 75.3% | 6.811% | 53.61% | 2.848% | 12.03%

## EGM PROJECT DURATION CALC. (hidden)
PM
|  | 13.3333 | 20 | 266.6667
INSTALLATIONS-CONVERSIONS-REMOVALS
| HRS/YR | EGMS | EGM/MONTH | EGM/WK | EGM/TECH/WK
TECHs | 4648 | 2324 | 249.83 | 58.1 | 1.3833
PMs
SPECIAL PROJECTS
| 10560.8 | 5280.4 | 567.643 | 132.01 | 3.1431
FY 13 ACTUALS
|  | Headcount | Actuals
|  | Resource demand | Total | Installations | Field service | Prevent-maint. | Special Projects (Systems) | Admin
|  |  | 0.75303 | 0.068113 | 0.53613 | 0.028479 | 0.12031
| TECHS | 41 | 65707.28 | 4648 | 47951.28 | 2547.2 | 10560.8
| PM | 1 | 1644 | 1444 | 0 | 0 | 200
1
| EGM Capacity Demand (FY13 Actual) | 43 | 67351.28 | 6092 | 47951.28 | 2547.2 | 10760.8 | 0
| FS Capacity Demand - SAP Actual |  | 32.3804 | 2.9288 | 23.0535 | 1.2246 | 5.1735
| FS - Headcount Deficit/Surplus |  | 10.6196 | 1.5112 | 3.1865 | 4.9254 | -0.0034615
|  | Headcount conversion | 32.3804 | 2.9288 | 23.0535 | 1.2246 | 5.1735 | 32.3804
|  |  | 0.75303 | 0.068113 | 0.53613 | 0.028479 | 0.12031

## REF(locked) (hidden)
Team | Project Status | Stage | Stage Name | Task Name | Resource locked | Task code | Hours required typically | Project code | 1 | 1.001 | 1.001 | CasinoLink | CasinoLink |  | TEAM | PM | ACTIVE | FY14 | Week# | wk# | PERIOD | WK start | wk start (Monday) | WK end | MONTH | PERIOD | wk# | WE | month | Baseline
1 | ACTIVE | 1 | Initiation | Initiating | PM | 100 |  | 1100 | 2 | 1.002 | 1.002 | Advantage | Advantage | 1.001 | 1 | Elvio Beautemps | BACKLOG | 2013-09-29 | 1 | 1 | 1 | 2013-09-29 | 2013-09-30 | 2013-10-05 | OCT | 1 | 1 | 2013-10-05
1 | ACTIVE | 2 | Planning | Project Charter | PM | 200 |  | 1200 | 3 | 1.003 | 1.003 | SBX | SBX | 1.002 | 2 | Juan Di Feo | REQUEST | 2013-09-30 | 1 | 2 | 1 | 2013-10-06 | 2013-10-07 | 2013-10-12 | OCT | 1 | 2 | 2013-10-12
1 | ACTIVE | 2 | Planning | Project Plan | PM | 201 |  | 1201 |  | 1.004 | 1.004 | Cloud | Cloud | 1.003 | 3 | Horacio Garcia | HOLD | 2013-10-01 | 1 | 3 | 1 | 2013-10-13 | 2013-10-14 | 2013-10-19 | OCT | 1 | 3 | 2013-10-19
1 | ACTIVE | 2 | Planning | Procurement of parts | PM | 202 |  | 1202 |  | 1.005 | 1.005 | EZPay | EZPay/sbX Upgrades/Hot Fixes |  | 0 | Gustavo Schleider | PIPELINE | 2013-10-02 | 1 | 4 | 1 | 2013-10-20 | 2013-10-21 | 2013-10-26 | OCT | 1 | 4 | 2013-10-26
1 | ACTIVE | 2 | Planning | Procurement of parts | SA | 203 |  | 1203 |  | 1.006 | 1.006 | Interactive | Interactive |  | 0 | Fernando Pagani | COMPLETED | 2013-10-03 | 1 | 5 | 2 | 2013-10-27 | 2013-10-28 | 2013-11-02 | NOV | 2 | 5 | 2013-11-02
1 | ACTIVE | 2 | Planning | Monitor progress & contract signature | PM | 204 |  | 1204 |  | 1.007 | 1.007 | TITO | TITO |  |  |  | CANCELLED | 2013-10-04 | 1 | 6 | 2 | 2013-11-03 | 2013-11-04 | 2013-11-09 | NOV | 2 | 6 | 2013-11-09
1 | ACTIVE | 3 | Execution | PM | PM | 300 |  | 1300 |  | 1.008 | 1.008 | UGA | UGA |  |  |  |  | 2013-10-05 | 1 | 7 | 2 | 2013-11-10 | 2013-11-11 | 2013-11-16 | NOV | 2 | 7 | 2013-11-16
1 | ACTIVE | 3 | Execution | SE | SE | 301 |  | 1301 |  | 1.009 |  | Support | [5 empty] | 2013-10-06 | 2 | 8 | 2 | 2013-11-17 | 2013-11-18 | 2013-11-23 | NOV | 2 | 8 | 2013-11-23
1 | ACTIVE | 3 | Execution | TRN | TRN | 302 |  | 1302 |  | 1.01 |  | Managed Services | [5 empty] | 2013-10-07 | 2 | 9 | 3 | 2013-11-24 | 2013-11-25 | 2013-11-30 | DEC | 3 | 9 | 2013-11-30
1 | ACTIVE | 4 | GoLive | PM | PM | 400 |  | 1400 | 0 | 0 |  | needs update | [5 empty] | 2013-10-08 | 2 | 10 | 3 | 2013-12-01 | 2013-12-02 | 2013-12-07 | DEC | 3 | 10 | 2013-12-07
1 | ACTIVE | 4 | GoLive | SE | SE | 401 |  | 1401 | [9 empty] | 2013-10-09 | 2 | 11 | 3 | 2013-12-08 | 2013-12-09 | 2013-12-14 | DEC | 3 | 11 | 2013-12-14
1 | ACTIVE | 4 | GoLive | TRN | TRN | 402 |  | 1402 | [9 empty] | 2013-10-10 | 2 | 12 | 3 | 2013-12-15 | 2013-12-16 | 2013-12-21 | DEC | 3 | 12 | 2013-12-21
1 | ACTIVE | 5 | Closing | PM | PM | 500 |  | 1500 | [9 empty] | 2013-10-11 | 2 | 13 | 3 | 2013-12-22 | 2013-12-23 | 2013-12-28 | DEC | 3 | 13 | 2013-12-28
2 | ACTIVE | 1 | Initiation | Initiating | PM | 100 |  | 2100 | [9 empty] | 2013-10-12 | 2 | 14 | 4 | 2013-12-29 | 2013-12-30 | 2014-01-04 | JAN | 4 | 14 | 2014-01-04
2 | ACTIVE | 2 | Planning | Project Charter | PM | 200 |  | 2200 | [9 empty] | 2013-10-13 | 3 | 15 | 4 | 2014-01-05 | 2014-01-06 | 2014-01-11 | JAN | 4 | 15 | 2014-01-11
2 | ACTIVE | 2 | Planning | Project Plan | PM | 201 |  | 2201 | [9 empty] | 2013-10-14 | 3 | 16 | 4 | 2014-01-12 | 2014-01-13 | 2014-01-18 | JAN | 4 | 16 | 2014-01-18
2 | ACTIVE | 2 | Planning | Procurement of parts | PM | 202 |  | 2202 | [9 empty] | 2013-10-15 | 3 | 17 | 4 | 2014-01-19 | 2014-01-20 | 2014-01-25 | JAN | 4 | 17 | 2014-01-25
2 | ACTIVE | 2 | Planning | Procurement of parts | SA | 203 |  | 2203 | [9 empty] | 2013-10-16 | 3 | 18 | 5 | 2014-01-26 | 2014-01-27 | 2014-02-01 | FEB | 5 | 18 | 2014-02-01
2 | ACTIVE | 2 | Planning | Monitor progress & contract signature | PM | 204 |  | 2204 | [9 empty] | 2013-10-17 | 3 | 19 | 5 | 2014-02-02 | 2014-02-03 | 2014-02-08 | FEB |  | 19 | 2014-02-08
2 | ACTIVE | 3 | Execution | PM | PM | 300 |  | 2300 | [9 empty] | 2013-10-18 | 3 | 20 | 5 | 2014-02-09 | 2014-02-10 | 2014-02-15 | FEB | 5 | 20 | 2014-02-15
2 | ACTIVE | 3 | Execution | SE | SE | 301 |  | 2301 | [9 empty] | 2013-10-19 | 3 | 21 | 5 | 2014-02-16 | 2014-02-17 | 2014-02-22 | FEB | 5 | 21 | 2014-02-22
2 | ACTIVE | 3 | Execution | TRN | TRN | 302 |  | 2302 | [9 empty] | 2013-10-20 | 4 | 22 | 6 | 2014-02-23 | 2014-02-24 | 2014-03-01 | MAR | 6 | 22 | 2014-03-01
2 | ACTIVE | 4 | GoLive | PM | PM | 400 |  | 2400 | [9 empty] | 2013-10-21 | 4 | 23 | 6 | 2014-03-02 | 2014-03-03 | 2014-03-08 | MAR | 6 | 23 | 2014-03-08
2 | ACTIVE | 4 | GoLive | SE | SE | 401 |  | 2401 | [9 empty] | 2013-10-22 | 4 | 24 | 6 | 2014-03-09 | 2014-03-10 | 2014-03-15 | MAR | 6 | 24 | 2014-03-15
2 | ACTIVE | 4 | GoLive | TRN | TRN | 402 |  | 2402 | [9 empty] | 2013-10-23 | 4 | 25 | 6 | 2014-03-16 | 2014-03-17 | 2014-03-22 | MAR | 6 | 25 | 2014-03-22
2 | ACTIVE | 5 | Closing | PM | PM | 500 |  | 2500 | [9 empty] | 2013-10-24 | 4 | 26 | 6 | 2014-03-23 | 2014-03-24 | 2014-03-29 | MAR | 6 | 26 | 2014-03-29
3 | ACTIVE | 1 | Initiation | Initiating | PM | 100 |  | 3100 | [9 empty] | 2013-10-25 | 4 | 27 | 7 | 2014-03-30 | 2014-03-31 | 2014-04-05 | APR | 7 | 27 | 2014-04-05
3 | ACTIVE | 2 | Planning | Project Charter | PM | 200 |  | 3200 | [9 empty] | 2013-10-26 | 4 | 28 | 7 | 2014-04-06 | 2014-04-07 | 2014-04-12 | APR | 7 | 28 | 2014-04-12
3 | ACTIVE | 2 | Planning | Project Plan | PM | 201 |  | 3201 | [9 empty] | 2013-10-27 | 5 | 29 | 7 | 2014-04-13 | 2014-04-14 | 2014-04-19 | APR | 7 | 29 | 2014-04-19
3 | ACTIVE | 2 | Planning | Procurement of parts | PM | 202 |  | 3202 | [9 empty] | 2013-10-28 | 5 | 30 | 7 | 2014-04-20 | 2014-04-21 | 2014-04-26 | APR | 7 | 30 | 2014-04-26
3 | ACTIVE | 2 | Planning | Procurement of parts | SA | 203 |  | 3203 | [9 empty] | 2013-10-29 | 5 | 31 | 8 | 2014-04-27 | 2014-04-28 | 2014-05-03 | MAY | 8 | 31 | 2014-05-03
3 | ACTIVE | 2 | Planning | Monitor progress & contract signature | PM | 204 |  | 3204 | [9 empty] | 2013-10-30 | 5 | 32 | 8 | 2014-05-04 | 2014-05-05 | 2014-05-10 | MAY | 8 | 32 | 2014-05-10
3 | ACTIVE | 3 | Execution | PM | PM | 300 |  | 3300 | [9 empty] | 2013-10-31 | 5 | 33 | 8 | 2014-05-11 | 2014-05-12 | 2014-05-17 | MAY | 8 | 33 | 2014-05-17
3 | ACTIVE | 3 | Execution | SE | SE | 301 |  | 3301 | [9 empty] | 2013-11-01 | 5 | 34 | 8 | 2014-05-18 | 2014-05-19 | 2014-05-24 | MAY | 8 | 34 | 2014-05-24
3 | ACTIVE | 3 | Execution | TRN | TRN | 302 |  | 3302 | [9 empty] | 2013-11-02 | 5 | 35 | 9 | 2014-05-25 | 2014-05-26 | 2014-05-31 | JUN | 9 | 35 | 2014-05-31
3 | ACTIVE | 4 | GoLive | PM | PM | 400 |  | 3400 | [9 empty] | 2013-11-03 | 6 | 36 | 9 | 2014-06-01 | 2014-06-02 | 2014-06-07 | JUN | 9 | 36 | 2014-06-07
3 | ACTIVE | 4 | GoLive | SE | SE | 401 |  | 3401 | [9 empty] | 2013-11-04 | 6 | 37 | 9 | 2014-06-08 | 2014-06-09 | 2014-06-14 | JUN | 9 | 37 | 2014-06-14
3 | ACTIVE | 4 | GoLive | TRN | TRN | 402 |  | 3402 | [9 empty] | 2013-11-05 | 6 | 38 | 9 | 2014-06-15 | 2014-06-16 | 2014-06-21 | JUN | 9 | 38 | 2014-06-21
3 | ACTIVE | 5 | Closing | PM | PM | 500 |  | 3500 | [9 empty] | 2013-11-06 | 6 | 39 | 9 | 2014-06-22 | 2014-06-23 | 2014-06-28 | JUN | 9 | 39 | 2014-06-28
0 | BACKLOG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2013-11-07 | 6 | 40 | 10 | 2014-06-29 | 2014-06-30 | 2014-07-05 | JUL | 10 | 40 | 2014-07-05
0 | REQUEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2013-11-08 | 6 | 41 | 10 | 2014-07-06 | 2014-07-07 | 2014-07-12 | JUL | 10 | 41 | 2014-07-12
0 | HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2013-11-09 | 6 | 42 | 10 | 2014-07-13 | 2014-07-14 | 2014-07-19 | JUL | 10 | 42 | 2014-07-19
0 | PIPELINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2013-11-10 | 7 | 43 | 10 | 2014-07-20 | 2014-07-21 | 2014-07-26 | JUL | 10 | 43 | 2014-07-26
0 | COMPLETED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2013-11-11 | 7 | 44 | 11 | 2014-07-27 | 2014-07-28 | 2014-08-02 | AUG | 11 | 44 | 2014-08-02
0 | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2013-11-12 | 7 | 45 | 11 | 2014-08-03 | 2014-08-04 | 2014-08-09 | AUG | 11 | 45 | 2014-08-09
[18 empty] | 2013-11-13 | 7 | 46 | 11 | 2014-08-10 | 2014-08-11 | 2014-08-16 | AUG | 11 | 46 | 2014-08-16
[18 empty] | 2013-11-14 | 7 | 47 | 11 | 2014-08-17 | 2014-08-18 | 2014-08-23 | AUG | 11 | 47 | 2014-08-23
[18 empty] | 2013-11-15 | 7 | 48 | 12 | 2014-08-24 | 2014-08-25 | 2014-08-30 | SEP | 12 | 48 | 2014-08-30
[18 empty] | 2013-11-16 | 7 | 49 | 12 | 2014-08-31 | 2014-09-01 | 2014-09-06 | SEP | 12 | 49 | 2014-09-06
[18 empty] | 2013-11-17 | 8 | 50 | 12 | 2014-09-07 | 2014-09-08 | 2014-09-13 | SEP | 12 | 50 | 2014-09-13
[18 empty] | 2013-11-18 | 8 | 51 | 12 | 2014-09-14 | 2014-09-15 | 2014-09-20 | SEP | 12 | 51 | 2014-09-20
[18 empty] | 2013-11-19 | 8 | 52 | 12 | 2014-09-21 | 2014-09-22 | 2014-09-27 | SEP | 12 | 52 | 2014-09-27
[18 empty] | 2013-11-20 | 8
[18 empty] | 2013-11-21 | 8
[18 empty] | 2013-11-22 | 8
[18 empty] | 2013-11-23 | 8
[18 empty] | 2013-11-24 | 9
[18 empty] | 2013-11-25 | 9
[18 empty] | 2013-11-26 | 9
[18 empty] | 2013-11-27 | 9
[18 empty] | 2013-11-28 | 9
[18 empty] | 2013-11-29 | 9
[18 empty] | 2013-11-30 | 9
[18 empty] | 2013-12-01 | 10
[18 empty] | 2013-12-02 | 10
[18 empty] | 2013-12-03 | 10
[18 empty] | 2013-12-04 | 10
[18 empty] | 2013-12-05 | 10
[18 empty] | 2013-12-06 | 10
[18 empty] | 2013-12-07 | 10
[18 empty] | 2013-12-08 | 11
[18 empty] | 2013-12-09 | 11
[18 empty] | 2013-12-10 | 11
[18 empty] | 2013-12-11 | 11
[18 empty] | 2013-12-12 | 11
[18 empty] | 2013-12-13 | 11
[18 empty] | 2013-12-14 | 11
[18 empty] | 2013-12-15 | 12
[18 empty] | 2013-12-16 | 12
[18 empty] | 2013-12-17 | 12
[18 empty] | 2013-12-18 | 12
[18 empty] | 2013-12-19 | 12
[18 empty] | 2013-12-20 | 12
[18 empty] | 2013-12-21 | 12
[18 empty] | 2013-12-22 | 13
[18 empty] | 2013-12-23 | 13
[18 empty] | 2013-12-24 | 13
[18 empty] | 2013-12-25 | 13
[18 empty] | 2013-12-26 | 13
[18 empty] | 2013-12-27 | 13
[18 empty] | 2013-12-28 | 13
[18 empty] | 2013-12-29 | 14
[18 empty] | 2013-12-30 | 14
[18 empty] | 2013-12-31 | 14
[18 empty] | 2014-01-01 | 14
[18 empty] | 2014-01-02 | 14
[18 empty] | 2014-01-03 | 14
[18 empty] | 2014-01-04 | 14
[18 empty] | 2014-01-05 | 15
[18 empty] | 2014-01-06 | 15
[18 empty] | 2014-01-07 | 15
[18 empty] | 2014-01-08 | 15
[18 empty] | 2014-01-09 | 15
[18 empty] | 2014-01-10 | 15
[18 empty] | 2014-01-11 | 15
[18 empty] | 2014-01-12 | 16
[18 empty] | 2014-01-13 | 16
[18 empty] | 2014-01-14 | 16
[18 empty] | 2014-01-15 | 16
[18 empty] | 2014-01-16 | 16
[18 empty] | 2014-01-17 | 16
[18 empty] | 2014-01-18 | 16
[18 empty] | 2014-01-19 | 17
[18 empty] | 2014-01-20 | 17
[18 empty] | 2014-01-21 | 17
[18 empty] | 2014-01-22 | 17
[18 empty] | 2014-01-23 | 17
[18 empty] | 2014-01-24 | 17
[18 empty] | 2014-01-25 | 17
[18 empty] | 2014-01-26 | 18
[18 empty] | 2014-01-27 | 18
[18 empty] | 2014-01-28 | 18
[18 empty] | 2014-01-29 | 18
[18 empty] | 2014-01-30 | 18
[18 empty] | 2014-01-31 | 18
[18 empty] | 2014-02-01 | 18
[18 empty] | 2014-02-02 | 19
[18 empty] | 2014-02-03 | 19
[18 empty] | 2014-02-04 | 19
[18 empty] | 2014-02-05 | 19
[18 empty] | 2014-02-06 | 19
[18 empty] | 2014-02-07 | 19
[18 empty] | 2014-02-08 | 19
[18 empty] | 2014-02-09 | 20
[18 empty] | 2014-02-10 | 20
[18 empty] | 2014-02-11 | 20
[18 empty] | 2014-02-12 | 20
[18 empty] | 2014-02-13 | 20
[18 empty] | 2014-02-14 | 20
[18 empty] | 2014-02-15 | 20
[18 empty] | 2014-02-16 | 21
[18 empty] | 2014-02-17 | 21
[18 empty] | 2014-02-18 | 21
[18 empty] | 2014-02-19 | 21
[18 empty] | 2014-02-20 | 21
[18 empty] | 2014-02-21 | 21
[18 empty] | 2014-02-22 | 21
[18 empty] | 2014-02-23 | 22
[18 empty] | 2014-02-24 | 22
[18 empty] | 2014-02-25 | 22
[18 empty] | 2014-02-26 | 22
[18 empty] | 2014-02-27 | 22
[18 empty] | 2014-02-28 | 22
[18 empty] | 2014-03-01 | 22
[18 empty] | 2014-03-02 | 23
[18 empty] | 2014-03-03 | 23
[18 empty] | 2014-03-04 | 23
[18 empty] | 2014-03-05 | 23
[18 empty] | 2014-03-06 | 23
[18 empty] | 2014-03-07 | 23
[18 empty] | 2014-03-08 | 23
[18 empty] | 2014-03-09 | 24
[18 empty] | 2014-03-10 | 24
[18 empty] | 2014-03-11 | 24
[18 empty] | 2014-03-12 | 24
[18 empty] | 2014-03-13 | 24
[18 empty] | 2014-03-14 | 24
[18 empty] | 2014-03-15 | 24
[18 empty] | 2014-03-16 | 25
[18 empty] | 2014-03-17 | 25
[18 empty] | 2014-03-18 | 25
[18 empty] | 2014-03-19 | 25
[18 empty] | 2014-03-20 | 25
[18 empty] | 2014-03-21 | 25
[18 empty] | 2014-03-22 | 25
[18 empty] | 2014-03-23 | 26
[18 empty] | 2014-03-24 | 26
[18 empty] | 2014-03-25 | 26
[18 empty] | 2014-03-26 | 26
[18 empty] | 2014-03-27 | 26
[18 empty] | 2014-03-28 | 26
[18 empty] | 2014-03-29 | 26
[18 empty] | 2014-03-30 | 27
[18 empty] | 2014-03-31 | 27
[18 empty] | 2014-04-01 | 27
[18 empty] | 2014-04-02 | 27
[18 empty] | 2014-04-03 | 27
[18 empty] | 2014-04-04 | 27
[18 empty] | 2014-04-05 | 27
[18 empty] | 2014-04-06 | 28
[18 empty] | 2014-04-07 | 28
[18 empty] | 2014-04-08 | 28
[18 empty] | 2014-04-09 | 28
[18 empty] | 2014-04-10 | 28
[18 empty] | 2014-04-11 | 28
[18 empty] | 2014-04-12 | 28
[18 empty] | 2014-04-13 | 29
[18 empty] | 2014-04-14 | 29
[18 empty] | 2014-04-15 | 29
[18 empty] | 2014-04-16 | 29
[18 empty] | 2014-04-17 | 29
[18 empty] | 2014-04-18 | 29
[18 empty] | 2014-04-19 | 29
[18 empty] | 2014-04-20 | 30
[18 empty] | 2014-04-21 | 30
[18 empty] | 2014-04-22 | 30
[18 empty] | 2014-04-23 | 30
[18 empty] | 2014-04-24 | 30
[18 empty] | 2014-04-25 | 30
[18 empty] | 2014-04-26 | 30
[18 empty] | 2014-04-27 | 31
[18 empty] | 2014-04-28 | 31
[18 empty] | 2014-04-29 | 31
[18 empty] | 2014-04-30 | 31
[18 empty] | 2014-05-01 | 31
[18 empty] | 2014-05-02 | 31
[18 empty] | 2014-05-03 | 31
[18 empty] | 2014-05-04 | 32
[18 empty] | 2014-05-05 | 32
[18 empty] | 2014-05-06 | 32
[18 empty] | 2014-05-07 | 32
[18 empty] | 2014-05-08 | 32
[18 empty] | 2014-05-09 | 32
[18 empty] | 2014-05-10 | 32
[18 empty] | 2014-05-11 | 33
[18 empty] | 2014-05-12 | 33
[18 empty] | 2014-05-13 | 33
[18 empty] | 2014-05-14 | 33
[18 empty] | 2014-05-15 | 33
[18 empty] | 2014-05-16 | 33
[18 empty] | 2014-05-17 | 33
[18 empty] | 2014-05-18 | 34
[18 empty] | 2014-05-19 | 34
[18 empty] | 2014-05-20 | 34
[18 empty] | 2014-05-21 | 34
[18 empty] | 2014-05-22 | 34
[18 empty] | 2014-05-23 | 34
[18 empty] | 2014-05-24 | 34
[18 empty] | 2014-05-25 | 35
[18 empty] | 2014-05-26 | 35
[18 empty] | 2014-05-27 | 35
[18 empty] | 2014-05-28 | 35
[18 empty] | 2014-05-29 | 35
[18 empty] | 2014-05-30 | 35
[18 empty] | 2014-05-31 | 35
[18 empty] | 2014-06-01 | 36
[18 empty] | 2014-06-02 | 36
[18 empty] | 2014-06-03 | 36
[18 empty] | 2014-06-04 | 36
[18 empty] | 2014-06-05 | 36
[18 empty] | 2014-06-06 | 36
[18 empty] | 2014-06-07 | 36
[18 empty] | 2014-06-08 | 37
[18 empty] | 2014-06-09 | 37
[18 empty] | 2014-06-10 | 37
[18 empty] | 2014-06-11 | 37
[18 empty] | 2014-06-12 | 37
[18 empty] | 2014-06-13 | 37
[18 empty] | 2014-06-14 | 37
[18 empty] | 2014-06-15 | 38
[18 empty] | 2014-06-16 | 38
[18 empty] | 2014-06-17 | 38
[18 empty] | 2014-06-18 | 38
[18 empty] | 2014-06-19 | 38
[18 empty] | 2014-06-20 | 38
[18 empty] | 2014-06-21 | 38
[18 empty] | 2014-06-22 | 39
[18 empty] | 2014-06-23 | 39
[18 empty] | 2014-06-24 | 39
[18 empty] | 2014-06-25 | 39
[18 empty] | 2014-06-26 | 39
[18 empty] | 2014-06-27 | 39
[18 empty] | 2014-06-28 | 39
[18 empty] | 2014-06-29 | 40
[18 empty] | 2014-06-30 | 40
[18 empty] | 2014-07-01 | 40
[18 empty] | 2014-07-02 | 40
[18 empty] | 2014-07-03 | 40
[18 empty] | 2014-07-04 | 40
[18 empty] | 2014-07-05 | 40
[18 empty] | 2014-07-06 | 41
[18 empty] | 2014-07-07 | 41
[18 empty] | 2014-07-08 | 41
[18 empty] | 2014-07-09 | 41
[18 empty] | 2014-07-10 | 41
[18 empty] | 2014-07-11 | 41
[18 empty] | 2014-07-12 | 41
[18 empty] | 2014-07-13 | 42
[18 empty] | 2014-07-14 | 42
[18 empty] | 2014-07-15 | 42
[18 empty] | 2014-07-16 | 42
[18 empty] | 2014-07-17 | 42
[18 empty] | 2014-07-18 | 42
[18 empty] | 2014-07-19 | 42
[18 empty] | 2014-07-20 | 43
[18 empty] | 2014-07-21 | 43
[18 empty] | 2014-07-22 | 43
[18 empty] | 2014-07-23 | 43
[18 empty] | 2014-07-24 | 43
[18 empty] | 2014-07-25 | 43
[18 empty] | 2014-07-26 | 43
[18 empty] | 2014-07-27 | 44
[18 empty] | 2014-07-28 | 44
[18 empty] | 2014-07-29 | 44
[18 empty] | 2014-07-30 | 44
[18 empty] | 2014-07-31 | 44
[18 empty] | 2014-08-01 | 44
[18 empty] | 2014-08-02 | 44
[18 empty] | 2014-08-03 | 45
[18 empty] | 2014-08-04 | 45
[18 empty] | 2014-08-05 | 45
[18 empty] | 2014-08-06 | 45
[18 empty] | 2014-08-07 | 45
[18 empty] | 2014-08-08 | 45
[18 empty] | 2014-08-09 | 45
[18 empty] | 2014-08-10 | 46
[18 empty] | 2014-08-11 | 46
[18 empty] | 2014-08-12 | 46
[18 empty] | 2014-08-13 | 46
[18 empty] | 2014-08-14 | 46
[18 empty] | 2014-08-15 | 46
[18 empty] | 2014-08-16 | 46
[18 empty] | 2014-08-17 | 47
[18 empty] | 2014-08-18 | 47
[18 empty] | 2014-08-19 | 47
[18 empty] | 2014-08-20 | 47
[18 empty] | 2014-08-21 | 47
[18 empty] | 2014-08-22 | 47
[18 empty] | 2014-08-23 | 47
[18 empty] | 2014-08-24 | 48
[18 empty] | 2014-08-25 | 48
[18 empty] | 2014-08-26 | 48
[18 empty] | 2014-08-27 | 48
[18 empty] | 2014-08-28 | 48
[18 empty] | 2014-08-29 | 48
[18 empty] | 2014-08-30 | 48
[18 empty] | 2014-08-31 | 49
[18 empty] | 2014-09-01 | 49
[18 empty] | 2014-09-02 | 49
[18 empty] | 2014-09-03 | 49
[18 empty] | 2014-09-04 | 49
[18 empty] | 2014-09-05 | 49
[18 empty] | 2014-09-06 | 49
[18 empty] | 2014-09-07 | 50
[18 empty] | 2014-09-08 | 50
[18 empty] | 2014-09-09 | 50
[18 empty] | 2014-09-10 | 50
[18 empty] | 2014-09-11 | 50
[18 empty] | 2014-09-12 | 50
[18 empty] | 2014-09-13 | 50
[18 empty] | 2014-09-14 | 51
[18 empty] | 2014-09-15 | 51
[18 empty] | 2014-09-16 | 51
[18 empty] | 2014-09-17 | 51
[18 empty] | 2014-09-18 | 51
[18 empty] | 2014-09-19 | 51
[18 empty] | 2014-09-20 | 51
[18 empty] | 2014-09-21 | 52
[18 empty] | 2014-09-22 | 52
[18 empty] | 2014-09-23 | 52
[18 empty] | 2014-09-24 | 52
[18 empty] | 2014-09-25 | 52
[18 empty] | 2014-09-26 | 52
[18 empty] | 2014-09-27 | 52
Stage data validation

## System Sales Report (hidden)
From: McBride.Mike
Sent: Friday, March 14, 2014 8:49 PM
To: Aldana.Maria; Baque.Luis; Bogard.Marina; Carter.Debbie; Corio.Esteban; Derifield.Rebecca; Fernandez.Nancy; Florio.Monica; Gill.David; Gill.Sabby; LaMantia.Kelly; Martinez.Ramon; Martinez.Toni; McBride.Mike; Pagani.Fernando; Rivera.Domingo; Rodenberg.Otto; Roth.Janine; Schleider.Gustavo; Stewart.Chris; Vazquez.Elizabeth; Walzer.Eric; Wiedemer.Mark; Willis.Mike
Subject: WE 03/14/2014 - System Sales Report, SOLAC & MEX
WE 03/14/2014 - System Sales Report, SOLAC & MEX
Current Quarter - Key Deals
· <image001.gif> Casino Club Licensing (OPP65208/OPP57504/OPP66637)
o WHAT: Billing of CIESA EzPay licenses, based on additional licenses added as per monthly screenshots.
o FORECASTED: Q2 - 64k
o STATUS: 3/14/2014 - Finance completed exchange calculation, detailed proposal updated by presales, sent to OA for order creation. Awaiting SO.
o NEXT STEP: Deliver order for signature week of 3/10, 3/21.
o OWNER: Fernando P (PRESALES)
· Peru - Advantage Bonusing - Samcorp (OPP62945/OPP66700)
o WHAT: Samcorp is purchasing Xtra Credit and Point Play for 3 of their properties.
o FORECASTED: Q2 - 482k
o STATUS: 3/12/2014 - Installation completed and SDIs were signed.
o NEXT STEP: COMPLETE.
o OWNER: Juan di Feo (PMO)
<image002.png>
Next Quarter - Key Deals
· Peru - Advantage Bonusing - Samcorp Newport Properties (OPP66705)
o WHAT: Samcorp is purchasing Xtra Credit and Point Play for their remote properties.
o FORECASTED: Q3 - 757k
o STATUS: 3/14/2014 - Menu codes on order, Sam confirmed install on 03/31, contract is signed.
o NEXT STEP: Install and SDI (ETA 03/31).
o OWNER: Juan di Feo (PMO)
· Peru - sbX - Samcorp (OPP55020/OPP71248)
o WHAT: Samcorp is implementing sbX, 70 EGMs in 2 sites.
o FORECASTED: Q3 15k/mo recurring, 79k Install Services
o STATUS: 3/13/2014 - Contract sent and pending Sam signature - install date is now in April 23rd (pending parts order).
o NEXT STEP: Contracts Signature, Parts Order.
o OWNER: Nancy F(Contracts), Juan di Feo (PMO).
· Star Bay Casino (Latin Gaming) - Casino Link - Panama (OPP55230)
o WHAT: New Casino opening, w/112 IGT egms, Casinolink, sbX
o FORECASTED: 302k Q3 (05/17 Go-Live)
o STATUS 3/12/2014 - Contract has been signed , weekly follow call is now scheduled to track pending items. Parts orders and shipping prep in progress.
o NEXT STEP: Weekly progress meeting; Used part shipment has arrived to Panama - New parts shipment in progress.
o OWNERS: Elvio Beautemps (Order/Shipments)
POST-SALE Issues and Key Projects
· Mendoza Roadshow
o WHAT: A seminar in Q3 for Argentina Regulators and Chilean operators (2 separate events), to deep-dive on sbX products.
o STATUS: 3/14/2014 - Project team is defined, working on agenda and logistics of project.
o NEXT STEP: Meeting next week to redefine scope.
o OWNER: Fernando P(PRESALES)
· <image001.gif> Casino Club Seminar
o WHAT: Vision and Roadmap session with entire CC DMU. We need to secure commitment and planning from both IGT and CC to deliver a product refresh across Casino Club's operations.
o STATUS: 3/14/2014 - Currently defining best date for CC staff, 2nd or 3rd week of May.
o NEXT STEP: Craft agenda and formal invitations.
o OWNER: Mike M(PRESALES)
· Telavisa sbX - Operation Cloud
o WHAT: Working on a commitment to migrate Televisa's 8 sbX to Cloud to improve their service level and reduce our opex to support.
o STATUS: 3/13/2014 - Reviewing proposal with Lucas.
o NEXT STEP: Submit proposal and schedule EBC visit.
o OWNER: Mike M(PRESALES)
Samcorp - CasinoView Project
o WHAT: The CasinoView initiative provides data analysis for customers. Samcorp would like to participate in the program as a partner.
o STATUS: 3/12/2014 - As per Sam, IT staff is working with CasinoView team on technical details, to close contract. Samcorp's IT team are currently working on Bonusing/sbX which may cause some delays on their end. They are closing one project at a time.
o NEXT STEP: Review agreement with Customer when complete.
o OWNER: Michael Tsai (CASINOVIEW) and Gabriela Alonso (Contracts)
HOMOLOGATION Projects
· PERU - Advantage Homologation
o WHAT: The homologation of the web interface to MINCETUR (peruvian regulator) has been in progress since 2012. The interface was developed by Samcorp, but must pass through IGT PA and GLI certification
o STATUS: 3/6/2014 - Peru Executables 1.0 HF1 was submitted to GLI on 3/3.
o NEXT STEPS: GLI approval & Secondary (target 03/28) - then 9.1 executable submission.
o OWNER: Mike McBride (PRESALES)
· <image001.gif> BOLIVIA - CMS
o WHAT: Bolivian regulations have been implemented and requirements for CMS set.
o STATUS: 3/14/2014 - We need to review the data export requirements; will they need an interface or will a simple report suffice?.
o NEXT STEP: Reviewing export req's with Product Management and Compliance. Once GLI testing is complete (target 04/01) - deliver approvals to regulator. We will schedule a roadshow for Bolivian customers based on approval timelines on Games and Systems.
o OWNER: Mike McBride (PRESALES)

## SFDC import (pipeline) (hidden)
pipeline# | Opp Num | Product Name | Product Family | Account Name | Install At | InstallAt Nbr | Install Date | Opportunity Name | Opportunity Owner | Cost Center | Parent Account | SAP Parent Account Customer Num | Billing/Mailing City | Billing/Mailing Country | Probability (%) | Closed | Won | Stage | Forecast Category | Created Date | Close Date | Close Month | Install Fiscal Quarter | Install Fiscal Period | Opportunity Quantity | Amount Currency | Amount | Expected Revenue Currency | Expected Revenue | Systems Amount Currency | Systems Amount | Opportunity Notes | Next Step | Opp Num
1 | OPP69496 | EZ Pay Standalone | Systems | Boldt S.A. | Boldt S.A. | 3101056 | 2014-01-27 | Boldt - 15 lic MDQ | Leonardo Sosa | 100321 - Latin America | Boldt | 3700794 | Capital Federal | Argentina | 100 | 1 | 1 | Closed Won | Closed | 2014-01-08 | 2014-01-23 | 2014-01-01 | Q2 F14 | Feb F14 | 15 | USD | 4387.5 | USD | 4387.5 | USD | 4387.5 |  | Following up with the Procurement Manager | OPP69496
2 | OPP63814 | Cloud Services | Cloud Services | Operadora Class S de RL de CV | Operadora Class S de RL de CV | 3108885 | 2014-01-31 | Operadora Class Cloud Mtey Viva Mexico | Marisol Sanchez |  | CLASS | 3700775 | Monterrey | Mexico | 100 | 1 | 1 | Closed Won | Closed | 2013-10-07 | 2014-01-17 | 2014-01-01 | Q2 F14 | Feb F14 | 241 | USD | 71200 | USD | 71200 | USD | 0 |  | SDI signed by customer on Jan9,13. 20 EGMs installed with cloud. Must be changed to closed won. | OPP63814
3 | OPP69484 | Professional Services - Enterprise Solutions | Professional Services | Operadora Class S de RL de CV | Operadora Class S de RL de CV | 3108885 | 2014-01-31 | SBx/Cloud Training | Lon O'Donnell | 100790 - Sales | CLASS | 3700775 | Monterrey | Mexico | 75 | 0 | 0 | Quote/Order Sent to Customer | Commit | 2014-01-08 | 2014-01-24 | 2014-01-01 | Q2 F14 | Feb F14 | 16 | USD | 4000 | USD | 3000 | USD | 0 |  |  | OPP69484
4 | OPP59036 | EZ Pay Standalone | Systems | Boldt S.A. | Boldt S.A. | 3101056 | 2014-02-11 | Boldt - 9 Licencias Moron | Leonardo Sosa | 100321 - Latin America | Boldt | 3700794 | Capital Federal | Argentina | 75 | 0 | 0 | Quote/Order Sent to Customer | Pipeline | 2013-06-11 | 2014-02-05 | 2014-02-01 | Q2 F14 | Feb F14 | 9 | USD | 2632.5 | USD | 1974.38 | USD | 2632.5 |  | Following up with the Procurement Manager | OPP59036
5 | OPP57584 | EZ Pay Standalone | Systems | Boldt S.A. | Boldt S.A. | 3101056 | 2014-02-12 | Boldt - 35 lic Moron | Leonardo Sosa | 100321 - Latin America | Boldt | 3700794 | Capital Federal | Argentina | 75 | 0 | 0 | Quote/Order Sent to Customer | Pipeline | 2013-04-30 | 2014-02-05 | 2014-02-01 | Q2 F14 | Feb F14 | 35 | USD | 10237.5 | USD | 7678.13 | USD | 10237.5 |  | Following up with the Procurement Manager | OPP57584
6 | OPP57504 | System - Other | Systems | Casino Club S.A. | Casino Club S.A. | 3700795 | 2014-02-18 | Casino Club - CTN Licenses | Florencia Bobbio | 100321 - Latin America |  |  | Buenos Aires | Argentina | 75 | 0 | 0 | Quote/Order Sent to Customer | Best Case | 2013-04-29 | 2014-02-11 | 2014-02-01 | Q2 F14 | Feb F14 | 25 | USD | 90000 | USD | 67500 | USD | 90000 | CTN installed. 06-01-2014: Will be invoice in January |  | OPP57504
7 | OPP66700 | Advantage Bonus | Systems | Golden Investment S.A. | Golden Investment S.A. | 3106312 | 2014-03-03 | Bonusing 870 XC y PP | Fernando Pagani | 100321 - Latin America | Samcorp es Peru | 3700765 | San Isidro | Peru | 100 | 1 | 1 | Closed Won | Closed | 2013-12-05 | 2014-01-17 | 2014-01-01 | Q2 F14 | Mar F14 | 1741 | USD | 329306.66 | USD | 329306.66 | USD | 313200 |  | Implementation. Customer has requested installation in March. | OPP66700
duplicate | OPP66700 | Advantage Bonus | Systems | Golden Investment S.A. | Golden Investment S.A. | 3106312 | 2014-03-03 | Bonusing 870 XC y PP | Fernando Pagani | 100321 - Latin America | Samcorp es Peru | 3700765 | San Isidro | Peru | 100 | 1 | 1 | Closed Won | Closed | 2013-12-05 | 2014-01-17 | 2014-01-01 | Q2 F14 | Mar F14 | 1741 | USD | 329306.66 | USD | 329306.66 | USD | 313200 |  | Implementation. Customer has requested installation in March. | OPP66700
8 | OPP70000 | EZ Pay Standalone | Systems | Casino Club S.A. | Casino Club S.A. | 3700795 | 2014-03-03 | CC - Licencias Adicionales EzPay 5013 a 5080 | Fernando Pagani | 100321 - Latin America |  |  | Buenos Aires | Argentina | 75 | 0 | 0 | Quote/Order Sent to Customer | Commit | 2014-01-22 | 2014-02-10 | 2014-02-01 | Q2 F14 | Mar F14 | 67 | USD | 18508.75 | USD | 13881.56 | USD | 18508.75 | Pending SO 06-01-2014: Pending SO Pending Negotiation |  | OPP70000
9 | OPP62945 | Advantage Bonus | Systems | Golden Gaming S.A. | Golden Gaming S.A. | 3106345 | 2014-03-10 | GG-Peru-Bonusing 388 | Katty Lopez | 100321 - Latin America | Samcorp es Peru | 3700765 | San Isidro | Peru | 100 | 1 | 1 | Closed Won | Closed | 2013-09-06 | 2014-01-17 | 2014-01-01 | Q2 F14 | Mar F14 | 777 | USD | 153386.66 | USD | 153386.66 | USD | 139680 |  | Implementation. Customer has requested install in March. | OPP62945
duplicate | OPP62945 | Advantage Bonus | Systems | Golden Gaming S.A. | Golden Gaming S.A. | 3106345 | 2014-03-10 | GG-Peru-Bonusing 388 | Katty Lopez | 100321 - Latin America | Samcorp es Peru | 3700765 | San Isidro | Peru | 100 | 1 | 1 | Closed Won | Closed | 2013-09-06 | 2014-01-17 | 2014-01-01 | Q2 F14 | Mar F14 | 777 | USD | 153386.66 | USD | 153386.66 | USD | 139680 |  | Implementation. Customer has requested install in March. | OPP62945
10 | OPP55020 | sbX Library Access | Systems | Golden Investment S.A. | Golden Investment S.A. | 3106312 | 2014-03-18 | GI-Peru-Sbx-50units | Fernando Pagani | 100321 - Latin America | Samcorp es Peru | 3700765 | San Isidro | Peru | 75 | 0 | 0 | Quote/Order Sent to Customer | Commit | 2013-02-15 | 2014-02-06 | 2014-02-01 | Q2 F14 | Mar F14 | 5401 | USD | 454448 | USD | 340836 | USD | 375048 |  | Signature was received on Nov. 26th. Waiting on signed finance agreement. | OPP55020
duplicate | OPP55020 | sbX Analytics | Systems | Golden Investment S.A. | Golden Investment S.A. | 3106312 | 2014-03-18 | GI-Peru-Sbx-50units | Fernando Pagani | 100321 - Latin America | Samcorp es Peru | 3700765 | San Isidro | Peru | 75 | 0 | 0 | Quote/Order Sent to Customer | Commit | 2013-02-15 | 2014-02-06 | 2014-02-01 | Q2 F14 | Mar F14 | 5401 | USD | 454448 | USD | 340836 | USD | 375048 |  | Signature was received on Nov. 26th. Waiting on signed finance agreement. | OPP55020
duplicate | OPP55020 | sbX Floor Manager | Systems | Golden Investment S.A. | Golden Investment S.A. | 3106312 | 2014-03-18 | GI-Peru-Sbx-50units | Fernando Pagani | 100321 - Latin America | Samcorp es Peru | 3700765 | San Isidro | Peru | 75 | 0 | 0 | Quote/Order Sent to Customer | Commit | 2013-02-15 | 2014-02-06 | 2014-02-01 | Q2 F14 | Mar F14 | 5401 | USD | 454448 | USD | 340836 | USD | 375048 |  | Signature was received on Nov. 26th. Waiting on signed finance agreement. | OPP55020
11 | OPP57219 | sbX Get Connected | Systems | Inmobiliaria Masaris Sac | Inmobiliaria Masaris Sac | 3307197 | 2014-03-21 | Masaris-Peru-Cloud | Katty Lopez | 100321 - Latin America |  |  | Piura | Peru | 75 | 0 | 0 | Quote/Order Sent to Customer | Best Case | 2013-04-19 | 2014-02-21 | 2014-02-01 | Q2 F14 | Mar F14 | 793 | USD | 225720 | USD | 169290 | USD | 225720 |  | Waiting on contract to be signed. Sent multiple follow up emails | OPP57219
12 | OPP53334 | Cloud Services | Cloud Services | Casino Rivera | Casino Rivera | 3305409 | 2014-04-01 | Cloud Rivera | Natalia Torres | 100321 - Latin America | Boldt | 3700794 | Rivera | Uruguay | 100 | 1 | 1 | Closed Won | Closed | 2012-12-21 | 2014-01-27 | 2014-01-01 | Q3 F14 | Apr F14 | 902 | USD | 202501 | USD | 202501 | USD | 0 | Jan 24th Got contract signature. Waiting for install date confirmation | Confirm install date | OPP53334
13 | OPP70115 | Cloud Services | Cloud Services | Sala de Esparcimiento | Sala de Esparcimiento | 3305455 | 2014-04-01 | Cloud Rivera Esparcimiento | Fernando Pagani | 100321 - Latin America |  |  | Rivera | Uruguay | 100 | 1 | 1 | Closed Won | Closed | 2014-01-26 | 2014-01-27 | 2014-01-01 | Q3 F14 | Apr F14 | 902 | USD | 202501 | USD | 202501 | USD | 0 | Jan 24th Got contract signature. Waiting for install date confirmation | Confirm install date | OPP70115
14 | OPP55656 | EZ Pay Standalone | Systems | La Cabana Beach & Raquet Club Hotel | La Cabana Beach & Raquet Club Hotel | 3108732 | 2014-04-28 | Glitz Promo Ticket Licence | Celene Sierra | 100321 - Latin America |  |  | Aruba | Aruba | 75 | 0 | 0 | Quote/Order Sent to Customer | Omitted | 2013-03-05 | 2014-04-07 | 2014-04-01 | Q3 F14 | May F14 | 223 | USD | 29757.5 | USD | 22318.13 | USD | 21937.5 |  | Customer has to pay remaining balance. Last installment should be on 08/15 | OPP55656
duplicate | OPP55656 | EZ Pay Standalone | Systems | La Cabana Beach & Raquet Club Hotel | La Cabana Beach & Raquet Club Hotel | 3108732 | 2014-04-28 | Glitz Promo Ticket Licence | Celene Sierra | 100321 - Latin America |  |  | Aruba | Aruba | 75 | 0 | 0 | Quote/Order Sent to Customer | Omitted | 2013-03-05 | 2014-04-07 | 2014-04-01 | Q3 F14 | May F14 | 223 | USD | 29757.5 | USD | 22318.13 | USD | 21937.5 |  | Customer has to pay remaining balance. Last installment should be on 08/15 | OPP55656
15 | OPP69279 | CasinoLink | Systems | Direccion General de | Direccion General de | 3101190 | 2014-05-15 | SPC Progressive 8 machines | Fernando Pagani | 100321 - Latin America |  |  | Montevideo | Uruguay | 75 | 0 | 0 | Quote/Order Sent to Customer | Best Case | 2013-12-27 | 2014-02-14 | 2014-02-01 | Q3 F14 | May F14 | 9 | USD | 40533.2 | USD | 30399.9 | USD | 40533.2 |  |  | OPP69279
16 | OPP55230 | sbX Library Access | Systems | Star Bay Casino | Star Bay Casino | 3114603 | 2014-05-21 | Star Bay Casino (Latin Gaming) - Casino Link | Nancy Fernandez Bennett |  | Latin Gaming |  | Panama City | Panama | 75 | 0 | 0 | Quote/Order Sent to Customer | Best Case | 2013-02-21 | 2014-02-10 | 2014-02-01 | Q3 F14 | May F14 | 77 | USD | 891888.52 | USD | 668916.39 | USD | 796288.52 |  | 1/24 Marcelo requested contract be resent for review. Rafael is sending Systems Contract, PSA and DDI for their review and signature | OPP55230
duplicate | OPP55230 | sbX Analytics | Systems | Star Bay Casino | Star Bay Casino | 3114603 | 2014-05-21 | Star Bay Casino (Latin Gaming) - Casino Link | Nancy Fernandez Bennett |  | Latin Gaming |  | Panama City | Panama | 75 | 0 | 0 | Quote/Order Sent to Customer | Best Case | 2013-02-21 | 2014-02-10 | 2014-02-01 | Q3 F14 | May F14 | 77 | USD | 891888.52 | USD | 668916.39 | USD | 796288.52 |  | 1/24 Marcelo requested contract be resent for review. Rafael is sending Systems Contract, PSA and DDI for their review and signature | OPP55230
duplicate | OPP55230 | CasinoLink | Systems | Star Bay Casino | Star Bay Casino | 3114603 | 2014-05-21 | Star Bay Casino (Latin Gaming) - Casino Link | Nancy Fernandez Bennett |  | Latin Gaming |  | Panama City | Panama | 75 | 0 | 0 | Quote/Order Sent to Customer | Best Case | 2013-02-21 | 2014-02-10 | 2014-02-01 | Q3 F14 | May F14 | 77 | USD | 891888.52 | USD | 668916.39 | USD | 796288.52 |  | 1/24 Marcelo requested contract be resent for review. Rafael is sending Systems Contract, PSA and DDI for their review and signature | OPP55230
duplicate | OPP55230 | Professional Services | Professional Services | Star Bay Casino | Star Bay Casino | 3114603 | 2014-05-21 | Star Bay Casino (Latin Gaming) - Casino Link | Nancy Fernandez Bennett |  | Latin Gaming |  | Panama City | Panama | 75 | 0 | 0 | Quote/Order Sent to Customer | Best Case | 2013-02-21 | 2014-02-10 | 2014-02-01 | Q3 F14 | May F14 | 77 | USD | 891888.52 | USD | 668916.39 | USD | 796288.52 |  | 1/24 Marcelo requested contract be resent for review. Rafael is sending Systems Contract, PSA and DDI for their review and signature | OPP55230
[27 empty] | 6828021.17 | 0 | 5482509.93 | 0 | 5651952.53
systems pipeline report -filtered
Copyright (c) 2000-2014 salesforce.com, inc. All rights reserved.
Confidential Information - Do Not Distribute
Generated By: Luis Baque Intriago 1/27/2014 3:27 PM
IGT

## SystemCapacityPlann. calculator (hidden)
Resources dedicated to system projects: |  | Hours baseline/yr (77%): |  |  |  | 40 | wks/yr | Hours baseline/yr (100%): |  |  | 52 | wks/yr | [28 empty] | 2080
| 3 | 4806 | [5 empty] | 6240 | [32 empty] | 1601.6
| 12 | 19224 | [5 empty] | 24960
| 3 | 4806 | [5 empty] | 6240
| 18 | 28836 | [5 empty] | 37440 | [15 empty] | Optimum Capacity
|  | Time on task per project , per role | [5 empty] | Max. output
Project duration | LAC projects | [#] = weeks required per project engagement (per role) |  |  |  | typical project duration: |  | [#] = 100% project capacity per role (max output in 40 weeks) |  |  |  | Historical Capacity - FY13 actuals | [5 empty] | FY14 - Demand forecast | [5 empty] | FY14 - Optimum capacity Total headcount needed (adjusted forecast) | [5 empty] | Hours / years (Productive (23% removed)) |  |  |  |  | Hours / years (overall)
Installs |  | PM | SE | TRN | Planning buffer | weeks | hours | PM | SE | TRN |  | YR | Month | PM | SE | TRN |  | Per Year | Month | PM | SE | TRN |  | YR | Month | PM | SE | TRN |  | YR | PM | SE | TRN |  | YR | PM | SE | TRN
12 | CasinoLink | 4.875 | 9.75 | 23.25 |  | 12 | 1515 | 8.2051 | 4.1026 | 1.7204 |  | 5 | 0.41667 | 60.94% | 121.9% | 290.6% | 4.7344 | 5 | 0.41667 | 60.94% | 121.9% | 290.6% | 4.7344 | 6 | 0.5 | 0.73125 | 1.4625 | 3.4875 | 5.6813 | 3 | 1171.4625 | 2342.925 | 5586.975 | 9101.3625 | 3 | 1171.4625 | 2342.925 | 5586.975 | 9101.3625
6 | Cloud | 3.5 | 5.5 | 3 |  | 6 | 480 | 11.4286 | 7.2727 | 13.3333 |  | 0 | 0 | 0% | 0% | 0% | 0 | 2 | 0.16667 | 17.5% | 27.5% | 15% | 0.6 | 3 | 0.25 | 0.2625 | 0.4125 | 0.225 | 0.9 | 2 | 420.525 | 660.825 | 360.45 | 1441.8 | 2 | 420.525 | 660.825 | 360.45 | 1441.8
2 | Interactive | 2 | 2 | 2 |  | 2 | 240 | 20 | 20 | 20 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Adv Modules | 2 | 2 | 2 |  | 2 | 240 | 20 | 20 | 20 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Advantage | 6.5 | 13 | 31 |  | 16 | 2020 | 6.1538 | 3.0769 | 1.2903 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
6 | EZPay Install | 3.5 | 5.5 | 3 |  | 6 | 480 | 11.4286 | 7.2727 | 13.3333 |  | 12 | 1 | 105% | 165% | 90% | 3.6 | 20 | 1.6667 | 175% | 275% | 150% | 6 | 6 | 0.5 | 0.525 | 0.825 | 0.45 | 1.8 | 12 | 841.05 | 1321.65 | 720.9 | 2883.6 | 12 | 841.05 | 1321.65 | 720.9 | 2883.6
6 | sbX - Media Mgr/Integrated | 3 | 8 | 6 |  | 6 | 680 | 13.3333 | 5 | 6.6667 |  | 6 | 0.5 | 45% | 120% | 90% | 2.55 | 8 | 0.66667 | 60% | 160% | 120% | 3.4 | 5 | 0.41667 | 0.375 | 1 | 0.75 | 2.125 | 6 | 600.75 | 1602 | 1201.5 | 3404.25 | 6 | 600.75 | 1602 | 1201.5 | 3404.25
6 | sbx Flr Mgr | 3.5 | 5.5 | 3 |  | 6 | 480 | 11.4286 | 7.2727 | 13.3333 |  | 3 | 0.25 | 26.25% | 41.25% | 22.5% | 0.9 | 5 | 0.41667 | 43.75% | 68.75% | 37.5% | 1.5 | 3 | 0.25 | 0.2625 | 0.4125 | 0.225 | 0.9 | 4 | 420.525 | 660.825 | 360.45 | 1441.8 | 4 | 420.525 | 660.825 | 360.45 | 1441.8
12 | Table Products | 4.5 | 10.5 | 16 |  | 12 | 1240 | 8.8889 | 3.8095 | 2.5 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Tournament Manager | 2 | 2 | 2 |  | 1 | 240 | 20 | 20 | 20 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Installs / headcount capacity | [10 empty] | 26 | 2.1667 | 2.3719 | 4.4813 | 4.9312 | 11.7844 | 40 | 3.3333 | 3.5719 | 6.5312 | 6.1313 | 16.2344 | 23 | 1.9167 | 2.1563 | 4.1125 | 5.1375 | 11.4062 | 27 | 3454.3125 | 6588.225 | 8230.275 | 18272.8125 | 27 | 3454.3125 | 6588.225 | 8230.275 | 18272.8125
| % - capacity by project type (Installs) | [12 empty] | 79.06% | 37.34% | 164.4% | 65.47% |  |  | 119.1% | 54.43% | 204.4% | 90.19% |  |  | 71.88% | 34.27% | 171.2% | 63.37% |  | 71.88% | 34.27% | 171.2% | 63.37% |  | 55.36% | 26.4% | 131.9% | 48.81% |  | Total upgrades delivered during FY13 (per manager count)
Upgrades | [40 empty] | Upgrades | sola | mex | mclac | total
10 | CasinoLink Upgrade | 3.375 | 7.875 | 12 |  | 10 | 930 | 11.8519 | 5.0794 | 3.3333 |  | 2 | 0.16667 | 16.88% | 39.38% | 60% | 1.1625 | 7 | 0.58333 | 59.06% | 137.8% | 210% | 4.0687 | 1 | 0.083333 | 0.084375 | 0.19688 | 0.3 | 0.58125 | 2 | 135.1688 | 315.3938 | 480.6 | 931.1625 | 2 | 135.1688 | 315.3938 | 480.6 | 931.1625 |  | CasinoLink Upgrade | 4 |  | 3 | 7
2 | Adv Module Upgrades | 2 | 2 | 2 |  | 2 | 240 | 20 | 20 | 20 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 1 | 0.083333 | 0.05 | 0.05 | 0.05 | 0.15 | 1 | 80.1 | 80.1 | 80.1 | 240.3 | 1 | 80.1 | 80.1 | 80.1 | 240.3 |  | Adv Module Upgrades | 0 |  |  | 0
12 | Adv Upgrades | 4.5 | 10.5 | 16 |  | 12 | 1240 | 8.8889 | 3.8095 | 2.5 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | Adv Upgrades | 0 |  |  | 0
4 | EZPay Upgrade | 2 | 4 | 2 |  | 4 | 320 | 20 | 10 | 20 |  | 5 | 0.41667 | 25% | 50% | 25% | 1 | 5 | 0.41667 | 25% | 50% | 25% | 1 | 1 | 0.083333 | 0.05 | 0.1 | 0.05 | 0.2 | 2 | 80.1 | 160.2 | 80.1 | 320.4 | 2 | 80.1 | 160.2 | 80.1 | 320.4 |  | EZPay Upgrade | 2 |  | 3 | 5
4 | sbx Upgrades | 2 | 4 | 2 |  | 4 | 320 | 20 | 10 | 20 |  | 10 | 0.83333 | 50% | 100% | 50% | 2 | 13 | 1.0833 | 65% | 130% | 65% | 2.6 | 1 | 0.083333 | 0.05 | 0.1 | 0.05 | 0.2 | 2 | 80.1 | 160.2 | 80.1 | 320.4 | 2 | 80.1 | 160.2 | 80.1 | 320.4 |  | sbx Upgrades | 2 | 9 | 2 | 13
4 | Table Products Upgrades | 2 | 4 | 2 |  | 4 | 320 | 20 | 10 | 20 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | Table Products Upgrades | 0 |  |  | 0
4 | Tournament Manager | 2 | 4 | 2 |  | 4 | 320 | 20 | 10 | 20 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | Tournament Manager | 0 |  |  | 0
| Total upgrades / headcount capacity | [10 empty] | 17 | 1.4167 | 0.91875 | 1.8938 | 1.35 | 4.1625 | 25 | 2.0833 | 1.4906 | 3.1781 | 3 | 7.6688 | 4 | 0.33333 | 0.23438 | 0.44688 | 0.45 | 1.1313 | 7 | 375.4688 | 715.8938 | 720.9 | 1812.2625 | 7 | 375.4688 | 715.8938 | 720.9 | 1812.2625 |  | Total Upgrades | 8 | 9 | 8 | 25
| % - capacity by project type (upgrades) | [12 empty] | 30.62% | 15.78% | 45% | 23.12% |  |  | 49.69% | 26.48% | 100% | 42.6% |  |  | 7.812% | 3.724% | 15% | 6.285% |  | 7.812% | 3.724% | 15% | 6.285% |  | 6.017% | 2.868% | 11.55% | 4.84%
Support
| Maint support- time on task- per incident, per SE | 0.05 | 0.71 | 0.125 |  |  | 35.4 | 800 | 56.338 | 320 |  | 326 | 27.1667 | 40.75% | 578.6% | 101.9% |  | 408 | 34 | 43.75% | 621.2% | 109.4% |  | 350 | 29.1667 | 0.4375 | 6.2125 | 1.0938 |  | 350 | 700.875 | 9952.425 | 1752.1875 | 12405.4875 | 350 | 700.875 | 9952.425 | 1752.1875 | 0
| Total support / headcount capacity | [10 empty] | 326 | 27.1667 | 0.4075 | 5.7865 | 1.0188 | 7.2127 | 408 | 34 | 0.4375 | 6.2125 | 1.0938 | 7.7437 | 350 | 29.1667 | 0.4375 | 6.2125 | 1.0938 | 7.7437 | 350 | 700.875 | 9952.425 | 1752.1875 | 12405.4875 | 350 | 700.875 | 9952.425 | 1752.1875 | 12405.4875
| % - capacity by project type (support) | [6 empty] | [#] = capacity of support per year, per resource | [5 empty] | 13.58% | 48.22% | 33.96% | 40.07% |  |  | 14.58% | 51.77% | 36.46% | 43.02% |  |  | 14.58% | 51.77% | 36.46% | 43.02% |  | 14.58% | 51.77% | 36.46% | 43.02% |  | 11.23% | 39.87% | 28.08% | 33.13%
Managed Services | [39 empty] | % of week | [5 empty] | hour
| 1. Weekly online/offline health check | 0.005 | 0.05 | 0.005 |  |  | 2.4 | 8000 | 800 | 8000 |  | 0 | 0 | 0% | 0% | 0% |  | 100 | 8.3333 | 1.25% | 12.5% | 1.25% |  | 100 | 8.3333 | 0.0125 | 0.125 | 0.0125 |  | 100 | 20.025 | 200.25 | 20.025 | 240.3 | 100 | 20.025 | 200.25 | 20.025 | 240.3 | 0.025 | 0.2 | 0.025 | 0.005 |  |  | 1
| 2. Weekly server health check | 0.005 | 0.05 | 0.005 |  |  | 2.4 | 8000 | 800 | 8000 |  | 0 | 0 | 0% | 0% | 0% |  | 100 | 8.3333 | 1.25% | 12.5% | 1.25% |  | 100 | 8.3333 | 0.0125 | 0.125 | 0.0125 |  | 100 | 20.025 | 200.25 | 20.025 | 240.3 | 100 | 20.025 | 200.25 | 20.025 | 240.3 | 0.05 | 0.005 | 0.025 | 0.005 |  |  | 2
| 3. Monthly floor mix changes (based on recommendation from pre-sales machines team) | 0.02 | 0.2 | 0.02 |  |  | 9.6 | 2000 | 200 | 2000 |  | 0 | 0 | 0% | 0% | 0% |  | 36 | 3 | 1.8% | 18% | 1.8% |  | 36 | 3 | 0.018 | 0.18 | 0.018 |  | 36 | 28.836 | 288.36 | 28.836 | 346.032 | 36 | 28.836 | 288.36 | 28.836 | 346.032 | 0.075 | 0.005 | 0.025 | 0.005 |  |  | 3
| 4. Monthly game library updates | 0.02 | 0.2 | 0.02 |  |  | 9.6 | 2000 | 200 | 2000 |  | 0 | 0 | 0% | 0% | 0% |  | 36 | 3 | 1.8% | 18% | 1.8% |  | 36 | 3 | 0.018 | 0.18 | 0.018 |  | 36 | 28.836 | 288.36 | 28.836 | 346.032 | 36 | 28.836 | 288.36 | 28.836 | 346.032 | 0.1 | 0.005 | 0.025 | 0.005 |  |  | 4
| Total support / headcount capacity | [10 empty] | 0 | 0 | 0.4075 | 5.7865 | 1.0188 | 7.2127 | 272 | 22.6667 | 0.4375 | 6.2125 | 1.0938 | 7.7437 | 272 | 22.6667 | 0.061 | 0.61 | 0.061 | 0.732 | 272 | 97.722 | 977.22 | 97.722 | 1172.664 | 272 | 97.722 | 977.22 | 97.722 | 1172.664 | 0.2 | [5 empty] | 8
| % - capacity by project type (support) | [12 empty] | 13.58% | 48.22% | 33.96% | 40.07% |  |  | 14.58% | 51.77% | 36.46% | 43.02% |  |  | 2.033% | 5.083% | 2.033% | 4.067% |  | 2.033% | 5.083% | 2.033% | 4.067% |  | 1.566% | 3.915% | 1.566% | 3.132%
60
7.8
| Total installs & upgrades headcount | [10 empty] | 43 | 3.5833 | 3.2906 | 6.375 | 6.2812 | 15.9469 | 65 | 5.4167 | 5.0625 | 9.7094 | 9.1313 | 23.9031 | 27 | 2.25 | 2.3906 | 4.5594 | 5.5875 | 12.5375 | 34 | 3829.7813 | 7304.1187 | 8951.175 | 20085.075 | 34 | 3829.7813 | 7304.1187 | 8951.175 | 20085.075
| Total Support & Managed Services | [10 empty] | 326 | 27.1667 | 0.815 | 11.573 | 2.0375 | 14.4255 | 680 | 56.6667 | 0.875 | 12.425 | 2.1875 | 15.4875 | 622 | 51.8333 | 0.4985 | 6.8225 | 1.1547 | 8.4757 | 622 | 798.597 | 10929.645 | 1849.9095 | 13578.1515 | 622 | 798.597 | 10929.645 | 1849.9095 | 13578.1515
| Overall Capacity (headcount) | [12 empty] | 4.1056 | 17.948 | 8.3187 | 30.3724 |  |  | 5.9375 | 22.1344 | 11.3188 | 39.3906 |  |  | 2.8891 | 11.3819 | 6.7422 | 21.0132 |  | 4628.3783 | 18233.7637 | 10801.0845 | 33663.2265 |  | 4628.3783 | 18233.7637 | 10801.0845 | 33663.2265
| Capacity% | [12 empty] | 136.9% | 149.6% | 277.3% | 168.7% |  |  | 197.9% | 184.5% | 377.3% | 218.8% |  |  | 96.3% | 94.85% | 224.7% | 116.7% |  | 96.3% | 94.85% | 224.7% | 116.7% |  | 74.17% | 73.05% | 173.1% | 89.91%
| Current staff supply | [12 empty] | 3 | 12 | 3 | 18 |  |  | 3 | 12 | 3 | 18 |  |  | 3 | 12 | 3 | 18 |  | 3 | 12 | 3 | 18 |  | 3 | 12 | 3 | 18
| staff deficit | [12 empty] | -1.1056 | -5.948 | -5.3187 | -12.3724 |  |  | -2.9375 | -10.1344 | -8.3188 | -21.3906 |  |  | 0.11087 | 0.61813 | -3.7422 | -3.0132 |  | 177.6217 | 990.2363 | -5995.0845 | -4827.2265 |  | 1611.6217 | 6726.2363 | -4561.0845 | 3776.7735
[31 empty] | 4806 | 19224 | 4806 | 28836 |  | 6240 | 24960 | 6240 | 37440
[31 empty] | 0.11087 | 0.61813 | -3.7422 | -3.0132 |  | 0.77482 | 3.2338 | -2.1928 | 1.8158
Max. capacity we are able to deliver per yr.& mo.
1.INSTALLS 26(yr) - 2(mo)
2.UPGRADES 17(yr) - 1(mo)
3.SUPPORT 326(yr) - 27(mo)
Goal:
  A.Maximize revenues (increase install, reducing upgrades)
  B.Reduce support
1.INSTALLS 36(yr) - 3(mo)
2.UPGRADES 0(yr) - 0(mo)
3.SUPPORT 408(yr) - 34(mo)
Current projects on 3DMETRIX and SFDC plus support demand (CPT)
1.INSTALLS 40(yr) - 3(mo)
2.UPGRADES 26(yr) - 2(mo)
3.SUPPORT 408(yr) - 34(mo)
Note on O7: LAC BASELINE: went over line by line with managers and these numbers will be use as 100% capacity baseline, based on the assumption that current resources allocated to SYSTEM PROJECTS at this level of activity, working 40 weeks per year roughly yields 100% - 150% capacity leaving us at 0 - 2 resources needed per role :
Note on V7: Demand source of information: 1. 3DM 2. SFDC 3. SUPPORT (CPT)
Note on AC7: Actual scenarios: 1. INSTALL CAPACITY (maximum installations capability) 2. UPGRADE CAPACITY (zero upgrades due to support demand requirements at 50%) 3. SUPPORT CAPACITY (34 per month / 408 per year ***not adjusted in this model)
Note on V15: 5 sbX Analytics 3 sbX get connected 0 sbX library access
Note on AC15: 5 sbX Analytics 3 sbX get connected 0 sbX library access
Note on V16: 2 sbX 3 sbX Floor Manager
Note on AC16: 2 sbX 3 sbX Floor Manager
Note on B22: 75% of ADV upgraades
Note on A35: Weekly time on task = - 1 hour per week (0.03) - 2 hour per week (0.05) - 3 hour per week (0.08) - 5 hour per week (0.13)
Note on B35: Weekly time on task = - 1 hour per week (0.03) - 2 hour per week (0.05) - 3 hour per week (0.08) - 5 hour per week (0.13)

## LAC-ProjectsDurationCalculator (hidden)
[29 empty] | Anticipated Sales Pipeline Requests |  |  |  | Work Availability
| PMs= | 3 |  | 40 | Weeks/yr baseline(77%) | [27 empty] | 52 | weeks - available per year.
| SEs= | 12 | [30 empty] | 4 | weeks - DTO//Holiday/FMLA
| TRNs= | 3 | [30 empty] | 5 | weeks - Admin/Periodic classes/on-line/special projects
|  | 18 | [30 empty] | 3 | weeks - Run Rate
[33 empty] | 40 | weeks - This represents 77% on project
|  | [#] = weeks required per project engagement (per role) |  |  |  | typical project duration: |  | [#] = 100% project capacity per role (max output in 40 weeks) |  |  | FY13 baseline Capacity (Supply) | [5 empty] | Demand forecast | [5 empty] | Actual demand (plug realistic scenarios) | [6 empty] | FORECAST - LAC FY14 Pipeline
ROW | Projects | PM | SE | TRN | buffer | weeks | hours | PM | SE | TRN | YR | Month | PM | SE | TRN |  | Per Year | Month | PM | SE | TRN |  | YR | Month | PM | SE | TRN |  |  | Per Year
86 | CasinoLink | 4.875 | 9.75 | 23.25 |  | 15 | 1515 | 8.2051 | 4.1026 | 1.7204 | 5 | 0.41667 | 60.94% | 121.9% | 290.6% | 4.7344 | 5 | 0.41667 | 60.94% | 121.9% | 290.6% | 4.7344 | 3 | 0.25 | 36.56% | 73.12% | 174.4% | 2.8406 |  | 1
97 | Cloud | 3.5 | 5.5 | 3 |  |  | 480 | 11.4286 | 7.2727 | 13.3333 | 0 | 0 | 0% | 0% | 0% | 0 | 2 | 0.16667 | 17.5% | 27.5% | 15% | 0.6 | 2 | 0.16667 | 17.5% | 27.5% | 15% | 0.6 |  | 5
185 | Interactive | 2 | 2 | 2 |  |  | 240 | 20 | 20 | 20 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  | 1
175 | Adv Modules | 2 | 2 | 2 |  |  | 240 | 20 | 20 | 20 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  | 0
110 | Advantage | 6.5 | 13 | 31 |  |  | 2020 | 6.1538 | 3.0769 | 1.2903 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  | 0
121 | EZPay Install | 3.5 | 5.5 | 3 |  |  | 480 | 11.4286 | 7.2727 | 13.3333 | 12 | 1 | 105% | 165% | 90% | 3.6 | 20 | 1.6667 | 175% | 275% | 150% | 6 | 18 | 1.5 | 157.5% | 247.5% | 135% | 5.4 |  | 8 |  |  |  |  | Count of Opp Num | Column Labels
165 | sbX - Media Mgr/Integrated | 3 | 8 | 6 |  |  | 680 | 13.3333 | 5 | 6.6667 | 6 | 0.5 | 45% | 120% | 90% | 2.55 | 8 | 0.66667 | 60% | 160% | 120% | 3.4 | 8 | 0.66667 | 60% | 160% | 120% | 3.4 |  | 5 | [5 empty] | FY13 | [11 empty] | FY13 Total | FY14 | [7 empty] | FY14 Total
121 | sbx Flr Mgr | 3.5 | 5.5 | 3 |  |  | 480 | 11.4286 | 7.2727 | 13.3333 | 3 | 0.25 | 26.25% | 41.25% | 22.5% | 0.9 | 5 | 0.41667 | 43.75% | 68.75% | 37.5% | 1.5 | 5 | 0.41667 | 43.75% | 68.75% | 37.5% | 1.5 |  | 0 |  |  |  |  | Row Labels | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep |  | Oct | Nov | Dec | Feb | Mar | May | Jun | Aug
133 | Table Products | 4.5 | 10.5 | 16 |  |  | 1240 | 8.8889 | 3.8095 | 2.5 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  | 0 |  |  |  |  | CasinoLink | [12 empty] | 5 |  |  |  |  | 1 |  |  |  | 1 | bar: FY13 Dec; FY13 Mar to FY13 Apr; FY13 Jun; FY13 Aug
175 | Tournament Manager | 2 | 2 | 2 |  |  | 240 | 20 | 20 | 20 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  | 0 |  |  |  |  | CasinoLink Upgrade | [13 empty] | 1 | [7 empty] | 1
| Total Projects | [9 empty] | 26 | 2.1667 | 2.3719 | 4.4813 | 4.9312 | 11.7844 | 40 | 3.3333 | 3.5719 | 6.5312 | 6.1313 | 16.2344 | 36 | 3 | 3.1531 | 5.7688 | 4.8187 | 13.7406 |  | 20 |  |  |  |  | Cloud | [13 empty] | 2 |  | 3 | [5 empty] | 5
[13 empty] | (headcount demand) | [18 empty] | FY 13 atual upgrades |  |  | Conversion | [12 empty] | 2 | bar: FY13 Jun; FY13 Sep
| Upgrades | [29 empty] | sola | mex | mclac |  | EZ Pay Standalone | 4 |  | 2 | 1 | 1 |  | 4 |  | 3 |  | 4 | 1 | 20 | 6 |  |  |  | 2 |  |  |  | 8
133 | CasinoLink Upgrade | 3.375 | 7.875 | 12 |  |  | 930 | 11.8519 | 5.0794 | 3.3333 | 2 | 0.16667 | 16.88% | 39.38% | 60% | 1.1625 | 8 | 0.66667 | 67.5% | 157.5% | 240% | 4.65 |  |  | 0% | 0% | 0% | 0 |  | 1 | 4 |  | 3 |  | Interactive | [14 empty] | 1 | [6 empty] | 1
175 | Adv Module Upgrades | 2 | 2 | 2 |  |  | 240 | 20 | 20 | 20 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  |  | 0% | 0% | 0% | 0 |  | 0 | 0 |  |  |  | Machine | 2 | 3 | 24 | 5 | 5 | 4 | 3 | 15 | 10 | 5 | 9 | 9 | 94 | 12 | 6 | 10 | 3 | 3 | 1 | 3 | 3 | 41
133 | Adv Upgrades | 4.5 | 10.5 | 16 |  |  | 1240 | 8.8889 | 3.8095 | 2.5 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  |  | 0% | 0% | 0% | 0 |  | 0 | 0 |  |  |  | sbx | FY13 Oct: 2 | 2
155 | EZPay Upgrade | 2 | 4 | 2 |  |  | 320 | 20 | 10 | 20 | 5 | 0.41667 | 25% | 50% | 25% | 1 | 5 | 0.41667 | 25% | 50% | 25% | 1 |  |  | 0% | 0% | 0% | 0 |  | 0 | 2 |  | 3 |  | sbX Analytics | FY13 Nov: 2; FY13 Feb: 2; FY13 Aug: 1 | 5 | 1 |  |  |  | 1 |  |  |  | 2
155 | sbx Upgrades | 2 | 4 | 2 |  |  | 320 | 20 | 10 | 20 | 10 | 0.83333 | 50% | 100% | 50% | 2 | 13 | 1.0833 | 65% | 130% | 65% | 2.6 |  |  | 0% | 0% | 0% | 0 |  | 0 | 2 | 9 | 2 |  | sbX Floor Manager | FY13 Mar: 1; FY13 Aug: 2 | 3
155 | Table Products Upgrades | 2 | 4 | 2 |  |  | 320 | 20 | 10 | 20 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  |  | 0% | 0% | 0% | 0 |  | 0 | 0 |  |  |  | sbX Get Connected | FY13 Aug: 3 | 3 |  | 1 | [6 empty] | 1
155 | Tournament Manager | 2 | 4 | 2 |  |  | 320 | 20 | 10 | 20 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0 |  |  | 0% | 0% | 0% | 0 |  | 0 | 0 |  |  |  | sbX Library Access | [15 empty] | 1 |  | 1 |  |  |  | 2
| Total Upgrades | [9 empty] | 17 | 1.4167 | 0.91875 | 1.8938 | 1.35 | 4.1625 | 26 | 2.1667 | 1.575 | 3.375 | 3.3 | 8.25 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 8 | 9 | 8 |  | sbX Upgrade | [12 empty] | 1 | bar: FY13 Mar
| Support | [33 empty] | Grand Total | 8 | 5 | 27 | 6 | 8 | 7 | 8 | 15 | 15 | 5 | 20 | 11 | 135 | 22 | 8 | 14 | 3 | 8 | 1 | 3 | 3 | 62
195 | Maint support- time on task- per incident, per SE | 0.21 | 0.71 | 0.21 |  |  | 45.2 | 190.4762 | 56.338 | 190.4762 | 326 | 27.1667 | 171.2% | 578.6% | 171.2% |  | 408 | 34 | 214.2% | 724.2% | 214.2% |  | 408 | 34 | 214.2% | 724.2% | 214.2%
| Total Support | [9 empty] | 326 | 27.1667 | 1.7115 | 5.7865 | 1.7115 | 9.2095 | 408 | 34 | 2.142 | 7.242 | 2.142 | 11.526 | 408 | 34 | 2.142 | 7.242 | 2.142 | 11.526
[#] = capacity of support per year, per resource
| Total project, upgrade & support - headcount demand | [9 empty] | 43 | 3.5833 | 5.0021 | 12.1615 | 7.9927 | 25.1564 | 66 | 5.5 | 7.2889 | 17.1483 | 11.5733 | 36.0104 | 36 | 3 | 5.2951 | 13.0108 | 6.9607 | 25.2666 |  | 21 | 83.72%
| Overall capacity % by role | [11 empty] | 166.7% | 101.3% | 266.4% | 139.8% |  |  | 243% | 142.9% | 385.8% | 200.1% |  |  | 176.5% | 108.4% | 232% | 140.4%
| staffing levels (red=deficit) | [11 empty] | -2.0021 | -0.1615 | -4.9927 | -7.1564 |  |  | -4.2889 | -5.1483 | -8.5733 | -18.0104 |  |  | -2.2951 | -1.0108 | -3.9607 | -7.2666
| # Headcount Needed | PM | SE | TRN | Total
ROW | Installations
86 | CasinoLink | 0.36563 | 0.73125 | 1.7437 | 2.8406
97 | Cloud | 0.175 | 0.275 | 0.15 | 0.6
185 | Interactive | 0 | 0 | 0 | 0
175 | Adv Modules | 0 | 0 | 0 | 0
110 | Advantage | 0 | 0 | 0 | 0
121 | EZPay Install | 1.575 | 2.475 | 1.35 | 5.4
165 | sbX - Media Mgr/Integrated | 0.6 | 1.6 | 1.2 | 3.4
121 | sbx Flr Mgr | 0.4375 | 0.6875 | 0.375 | 1.5
133 | Table Products | 0 | 0 | 0 | 0
175 | Tournament Manager | 0 | 0 | 0 | 0
| Total Projects | 3.1531 | 5.7688 | 4.8187 | 13.7406
Upgrades
133 | CasinoLink Upgrade | 0 | 0 | 0 | 0
175 | Adv Module Upgrades | 0 | 0 | 0 | 0
133 | Adv Upgrades | 0 | 0 | 0 | 0
155 | EZPay Upgrade | 0 | 0 | 0 | 0
155 | sbx Upgrades | 0 | 0 | 0 | 0
155 | Table Products Upgrades | 0 | 0 | 0 | 0
155 | Tournament Manager | 0 | 0 | 0 | 0
| Total Upgrades | 0 | 0 | 0 | 0
| support | 1.445 | 7.225 | 5.78 | 14.45
195
| Grand Total | 4.5981 | 12.9938 | 10.5988 | 28.1906
| ROLE | PM | SE | TRN | total
| Current Staffing Levels | 3 | 12 | 3 | 18
| Capacity of Current Staff (FY13 ACTUALS) | 153.3% | 108.3% | 353.3% | 156.6%
| Deficit of Current Staff | -1.5981 | -0.99375 | -7.5988 | -10.1906
WEEKS PER PROJECT PHASE AND ROLE (PER U.S. STANDARDS FOR A TYPICAL SYSTEM INSTALLATION TYPE)
Typical CasinoLink Installation
| CasinoLink | PM | SE | TRN |  |  | Total Hours for typical project of this type:
| Prep | 1.125 | 0 | 0 |  |  | 45
| Site Survey + Prep | 0.75 | 2.25 | 3 |  |  | 240
| Build | 0 | 1.5 | 3 |  |  | 180
| Installation/Config/Conversion | 0.75 | 1.5 | 3 |  |  | 210
| Trn / Set-Up | 1.5 | 1.5 | 6 |  |  | 360
| Go-Live | 0.75 | 2.25 | 5.25 |  |  | 330
| Follow-up | 0 | 0.75 | 3 |  |  | 150
| Total weeks Per Proj. | 4.875 | 9.75 | 23.25 |  |  | 1515
| Projects Per Year (per resource) | 8.2051 | 4.1026 | 1.7204
75% of Advantage installation
Typical Cloud Installation
| Cloud | PM | SE | TRN
| Site Survey | 1 | 1 | 1 |  |  | 120
| Build |  | 1 |  |  |  | 40
| Installation | 0.5 | 0.5 |  |  |  | 40
| Configuration/Training | 1 | 1 | 1 |  |  | 120
| Go-Live | 1 | 2 | 1 |  |  | 160
| Total weeks Per Proj. | 3.5 | 5.5 | 3 |  |  | 480
| Projects Per Year (per resource) | 11.4286 | 7.2727 | 13.3333
Typical Advantage Installation (MA/IVS/PM/CTA/TM)
| Advantage | PM | SE | TRN
| Prep | 1.5 |  |  |  |  | 60
| Site Survey + Prep | 1 | 3 | 4 |  |  | 320
| Build |  | 2 | 4 |  |  | 240
| Installation/Config/Conversion | 1 | 2 | 4 |  |  | 280
| Trn / Set-Up | 2 | 2 | 8 |  |  | 480
| Go-Live | 1 | 3 | 7 |  |  | 440
| Follow-up |  | 1 | 4 |  |  | 200
| Total weeks Per Proj. | 6.5 | 13 | 31 |  |  | 2020
| Projects Per Year (per resource) | 6.1538 | 3.0769 | 1.2903
Typical Adv. Module/EZPay/sbX Installation
| sbx Flr Mgr | PM | SE | TRN
| Site Survey | 1 | 1 | 1 |  |  | 120
| Build |  | 1 |  |  |  | 40
| Installation | 0.5 | 0.5 |  |  |  | 40
| Configuration/Training | 1 | 1 | 1 |  |  | 120
| Go-Live | 1 | 2 | 1 |  |  | 160
| Total weeks Per Proj. | 3.5 | 5.5 | 3 |  |  | 480
| Projects Per Year (per resource) | 11.4286 | 7.2727 | 13.3333
Typical Adv. Upgrades - Table Products
| AdvantageUpgrades | PM | SE | TRN
| Prep | 1.5 | 2 | 4 |  |  | 300
| Build / Installation |  | 2 |  |  |  | 80
| Test Upgrade | 1 | 2 | 4 |  |  | 280
| Training | 1 | 1 | 4 |  |  | 240
| Upgrade | 1 | 3.5 | 4 |  |  | 340
| Follow-up | [5 empty] | 0
| Total weeks Per Proj. | 4.5 | 10.5 | 16 |  |  | 1240
| Projects Per Year (per resource) | 8.8889 | 3.8095 | 2.5
| 8.x - 8.x Upgrades | PM | SE | TRN
| Prep | 1 | 2 | 3 |  |  | 240
| Build / Installation | [5 empty] | 0
| Test Upgrade | 1 | 2 | 3 |  |  | 240
| OnLine Training | [5 empty] | 0
| Upgrade | 1 | 2 | 3 |  |  | 240
| Follow-up | [5 empty] | 0
| Total weeks Per Proj. | 3 | 6 | 9 |  |  | 720
| Projects Per Year (per resource) | 13.3333 | 6.6667 | 4.4444
| EZPay/sbX Upgrades/Hot Fixes | PM | SE | TRN
| Prep | 1 | 1 | 1 |  |  | 120
| Build |  | 1 |  |  |  | 40
| Training | [5 empty] | 0
| Go-Live | 1 | 2 | 1 |  |  | 160
| Total weeks Per Proj. | 2 | 4 | 2 |  |  | 320
| Projects Per Year (per resource) | 20 | 10 | 20
sbX - Media Mgr/Integrated
| sbX Media Mgr | PM | SE | TRN
| Prep | 1 | 2 | 2 |  |  | 200
| Build |  | 2 |  |  |  | 80
| Training | 1 | 2 | 2 |  |  | 200
| Go-Live | 1 | 2 | 2 |  |  | 200
| Total weeks Per Proj. | 3 | 8 | 6 |  |  | 680
| Projects Per Year (per resource) | 13.3333 | 5 | 6.6667
Tournament Mgr/Bonus/Interfaces
| Adv Modules | PM | SE | TRN
| Prep | 1 | 1 | 1 |  |  | 120
| Build | [5 empty] | 0
| Training | 0.5 | 0.5 | 0.5 |  |  | 60
| Go-Live | 0.5 | 0.5 | 0.5 |  |  | 60
| Total weeks Per Proj. | 2 | 2 | 2 |  |  | 240
| Projects Per Year (per resource) | 20 | 20 | 20
| Interactive | PM | SE | TRN
| Prep | 1 | 1 | 1 |  |  | 120
| Build | [5 empty] | 0
| Training | 0.5 | 0.5 | 0.5 |  |  | 60
| Go-Live | 0.5 | 0.5 | 0.5 |  |  | 60
| Total weeks Per Proj. | 2 | 2 | 2 |  |  | 240
| Projects Per Year (per resource) | 20 | 20 | 20
| Support (Maintenance) | PM | SE | TRN
| weeks per incident to resolve (*time -on-task per incident) | 0.14167 | 0.70833 | 0.56667 |  |  | 56.6667
0
0
0
| Total weeks Per incident to resolve | 0.14167 | 0.70833 | 0.56667 |  |  | 56.6667
| Support Per Year (per resource) | 282.3529 | 56.4706 | 70.5882
10615
| Maint support incidents per month |  | 34
| Maint support incidents per year |  | 408
| weeks per incident to resolve (*time -on-task per incident) |  | 0.70833
| support hours/week | 5.6667 | 28.3333 | 22.6667
Max. capacity we are able to deliver per yr.& mo.
1.INSTALLS 26(yr) - 2(mo)
2.UPGRADES 17(yr) - 1(mo)
3.SUPPORT 326(yr) - 27(mo)
Goal:
  A.eliminate support
  B. reduce support
1.INSTALLS 36(yr) - 3(mo)
2.UPGRADES 0(yr) - 0(mo)
3.SUPPORT 408(yr) - 34(mo)
Current projects on 3DMETRIX and SFDC plus support demand (CPT)
1.INSTALLS 40(yr) - 3(mo)
2.UPGRADES 26(yr) - 2(mo)
3.SUPPORT 408(yr) - 34(mo)
Note on O7: LAC BASELINE: went over line by line with managers and these numbers will be use as 100% capacity baseline, based on the assumption that current resources allocated to SYSTEM PROJECTS at this level of activity, working 40 weeks per year roughly yields 100% - 150% capacity leaving us at 0 - 2 resources needed per role :
Note on V7: Demand source of information: 1. 3DM 2. SFDC 3. SUPPORT (CPT)
Note on AC7: Actual scenarios: 1. INSTALL CAPACITY (maximum installations capability) 2. UPGRADE CAPACITY (zero upgrades due to support demand requirements at 50%) 3. SUPPORT CAPACITY (34 per month / 408 per year ***not adjusted in this model)
Note on V15: 5 sbX Analytics 3 sbX get connected 0 sbX library access
Note on AC15: 5 sbX Analytics 3 sbX get connected 0 sbX library access
Note on V16: 2 sbX 3 sbX Floor Manager
Note on AC16: 2 sbX 3 sbX Floor Manager
Note on B22: 75% of ADV upgraades
Note on B45: 75% of ADV installation
Note on B58: 75% of ADV upgrade
Note on C71: We have 2 PM's dedicated to System projects and 3 PM's dedicated to EGM projects
Note on E71: IGTAdmin: Edgar-EGM training
Note on E190: Follow-up: How to justify trainer's 80% of SE's time-on-task for maintenance support?
Note on D201: time on task per support was calculated by taking incidents on CPT report per month divided by 12 SE's, divided by 4 weeks.

## Rosario-WP
Plan v1 |  |  | On site W
|  | 2014-08-04 | 2014-08-18
Role | Resource | Week 1 | Week 2 | Hours | Buffer 30%
SE | Emanuel Dafonte | 4 | 40 | 44 | 57.2
Trainer | Katie Katayose | 4 | 40 | 44 | 57.2
PM | Elvio B. | 8 | 16 | 24 | 31.2
|  |  |  | 112 | 145.6 |  | 112 | 145.6
|  |  | Property Name: |  |  | Casino De Rosario Bonusing |  |  |  |  | Plan v2 - Work Plan v1
# of | # of | Average cost | Air needed? | Airfare Cost | Car Needed? | Car Rental | Lodging | Meals Per Diem** | Gas -Park | Misc | Taxi | Totals
days | travel | per trip | Y/N | 980 | Y/N |  |  |  |  | 20 |  | 1000
onsite | days | per day |  | 0 |  | 85 | 175 | 117 |  |  | 20 | 397
0
System Set Up***
5 | 2 | Trainer | Y | 980 | N |  | 1225 | 819 |  | 20 | 100 | 3144
5 | 0 | Systems Engineer | Y | 180 | N |  |  | 585 |  | 20 | 100 | 885
Notes: |  | * CS Slot Technician is dependent on # of games - Try to limit to no more than 10
|  | ** The 2010 base per diem rate is listed by default, this should be adjusted based at | [8 empty] | Grand Total: | 4029
the rate for the location where the work is located.
*** System Set up can be conducted at an IGT office. If so, there maybe be customer
travel charges in place of these travel expenses

## Crocs-WP
Plan v1 | [12 empty] | On site W |  | Install&Train |  |  | Support
|  | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15
Role | Resource | Week 1 | Week 2 |  |  | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Hours | Buffer 30%
SE | Pablo | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 40 | 40 | 24 | 5 | 40 | 40 | 5 | 16 | 32 | 256 | 332.8
SE | Adam | 2014-10-13: 2; 2014-10-20: 2; 2014-10-27: 2; 2014-11-03: 5; 2014-11-10: 5; 2014-11-17: 40; 2014-11-24: 40; 2014-12-01: 5; 2014-12-08: 16; 2014-12-15: 32 | 149 | 193.7
Trainer | Katie | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 24 | 5 | 8h | 40 | 5 | 16 | 32 | 143 | 185.9
Trainer | Roxana | 2014-11-10: 5; 2014-11-17: 8h; 2014-11-24: 40; 2014-12-01: 5; 2014-12-08: 16; 2014-12-15: 32 | 98 | 127.4
Tech | TBD Panama - Rafael | 2014-11-17: 40; 2014-11-24: 40; 2014-12-08: 16; 2014-12-15: 32 | 128 | 166.4
Tech | TBD Panama - Felix | 2014-11-17: 40; 2014-11-24: 40 | 80 | 104
Tech | TBD Panama - Taquir | 2014-11-17: 40; 2014-11-24: 40 | 80 | 104
PM | Elvio B. | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 24 | 10 | 40 | 40 | 8 | 16 | 32 | 197 | 256.1
[20 empty] | 1131 | 1470.3 | 1131 | 1470.3
HIGH LEVEL PLAN
The following dates will be valid if this Project Charter is Approved, the Requists are fulfilled and the Contract is signed before the Project Charter Expiration Date. | [19 empty] | 1038
Milestones
Contract Signed | 2014-07-24
Weekly Conferences IGT / Croc’s | Starting week of Aug 18, 2014 (Excluding weeks of Sep 1 and Sep 8)
Order Hardware | Week of Sep 15, 2014
Site Survey | TBD (Server Room ready/Cabling advanced)
Server Ready (Base Software included) | 2014-11-17
Cabling ready | 2014-11-24
All EGMs’ power Inputs available | 2014-11-24
All EGMs in their bases | 2014-12-01
Start working on EGMs | 2014-12-01
IGT Team starts working on the environment in Costa Rica | 2014-12-01
Training on site | Starting Dec 8, 2014
Testing | During the week of Dec 8, 2014
Go Live and Support | 2014-12-15
IGT Team leaving the property | 2014-12-19
Project Team | bar: 2014-08-18 to 2014-08-25
Role | Name | 2014-08-18: Organization; 2014-08-25: Contact Info
SE | Pablo Amarfil | 2014-08-18: IGT; 2014-08-25: Pablo.Amarfil@IGT.com
SE | Adam Evans | 2014-08-18: IGT; 2014-08-25: Adam.Evans@IGT.com
Trainer | Katie Katayose | 2014-08-18: IGT; 2014-08-25: Katie.Katayose@IGT.com
Trainer | Roxana Di Franco | 2014-08-18: IGT; 2014-08-25: Roxana.DiFranco@IGT.com
Technician | Rafael Serrano | 2014-08-18: IGT; 2014-08-25: Rafael.Serrano@IGT.com
Technician | Felix Diaz | 2014-08-18: IGT; 2014-08-25: Felix.Diaz@IGT.com
Technician | Takir Mendez | 2014-08-18: IGT; 2014-08-25: Takir.Mendez@IGT.com
PM | Elvio Beautemps | 2014-08-18: IGT; 2014-08-25: Elvio.Beautemps@IGT.com
Customer Info
Corporate Name | Croc’s Casino & Resort
Corporate Address | Jaco Beach, Costa Rica
Property Name | Croc’s Casino & Resort
Property Address | Jaco Beach, Costa Rica
Customer SAP Number | 3115270
Project Description
New Casino – 12hs of operation
Croc’s
Casinolink
· 150 machines (75IGT)
· ESMIBs
· Intelligence Suite: Cage and Pit
· Accounting/Player Tracking
· EzPay/IVS: Promo Ticket
· Media Manager with Service Window (All machines)
o UGA on Non-IGT games (75 EGMs)
· Random Riches
· POS Interface/AMI
Scope and Deliverables
Customer will install Casinolink solution for 150 machines.
· Site Survey
· Installation and configuration
o Casinolink/IVS – Promo Ticket
o Intelligence Suite
§ Cage
§ Pit: 2 with 19 tables
o Accounting/Player Tracking
o Media Manager/Service Windows
o Random Riches
o POS Interface/AMI
§ AGIL Sys
· Training
· Go Live Support

## Crocs T&E Estimate
|  |  | Property Name: |  |  | Crocs, Jaco Beach - Costa Rica
[5 empty] | Approximate # of games on the floor |  |  | 150
# of | # of | Average cost | Air needed? | Airfare Cost | Car Needed? | Car Rental | Lodging | Meals Per Diem** | Taxi | Misc | Mileage | Totals
days | travel | per trip | Y/N | 1500 | Y/N |  |  |  |  | 20 | 10 | 1530
onsite | days | per day |  | 0 |  | 70 | 147 | 109 | 15 |  | 0 | 341
Site Survey, Game Survey and Customer Site Review
2 | 2 | Systems Engineer | Y | 1500 | N |  | 588 | 436 | 60 | 20 | 10 | 2614
2 | 2 | Trainer | Y | 500 | N |  | 588 | 436 | 60 | 20 | 10 | 1614
2 | 2 | Project Manager | Y | 1500 | N |  | 588 | 436 | 60 | 20 | 10 | 2614
[8 empty] | 0 | 0 |  |  | 6842
[8 empty] | 0 | 0
0
System Set Up***
12 | 2 | Systems Engineer | Y | 1500 | N |  | 2058 | 1526 | 210 | 20 | 10 | 5324
12 | 2 | Systems Engineer | Y | 500 | N |  | 2058 | 1526 | 210 | 20 | 10 | 4324
8 | 2 | Trainer | Y | 500 | N |  | 1470 | 1090 | 150 | 20 | 10 | 3240
8 | 2 | Trainer | Y | 1500 | N |  | 1470 | 1090 | 150 | 20 | 10 | 4240
12 | 0 | Technician | Y | 400 | N |  | 1764 | 1308 | 180 | 20 | 10 | 3682
12 | 0 | Technician | Y | 400 | N |  | 1764 | 1308 | 180 | 20 | 10 | 3682
12 | 0 | Technician | Y | 400 | N |  | 1764 | 1308 | 180 | 20 | 10 | 3682
12 | 2 | Project Manager | Y | 1500 | N |  | 2058 | 1526 | 210 | 20 | 10 | 5324
33498
Support
8 | 2 | Systems Engineer | Y | 1500 | N |  | 1470 | 1090 | 150 | 20 | 10 | 4240
8 | 2 | Systems Engineer | Y | 500 | N |  | 1470 | 1090 | 150 | 20 | 10 | 3240
8 | 2 | Trainer | Y | 500 | N |  | 1470 | 1090 | 150 | 20 | 10 | 3240
8 | 2 | Trainer | Y | 1500 | N |  | 1470 | 1090 | 150 | 20 | 10 | 4240
8 | 0 | Technician | Y | 400 | N |  | 1176 | 872 | 120 | 20 | 10 | 2598
8 | 2 | Project Manager | Y | 1500 | N |  | 1470 | 1090 | 150 | 20 | 10 | 4240
21798
Notes: |  | * CS Slot Technician is dependent on # of games - Try to limit to no more than 10
|  | ** The 2010 base per diem rate is listed by default, this should be adjusted based at | [8 empty] | Grand Total: | 62138
the rate for the location where the work is located.
*** System Set up can be conducted at an IGT office. If so, there maybe be customer
travel charges in place of these travel expenses
Name:________________________________________ | [6 empty] | Phone: ________________
Title:_________________________________________
Signature:____________________________________ | [6 empty] | Date:__________________